- Digital Agenda for Europe (DAE)

- Digital Agenda Actions Implementation on European Commission and on National Level

- December 2012

- C ontents

- Action area/Pillar 1 – A vibrant digital single market …………………………………………………………………………………………………………………………………………… ………………………………………….2

- Action 1.1. Opening up access to content

- Action 1.2. Making online and cross border transactions straightforward

- Action 1.3 Building digital confidence

- Action 1.4 Reinforcing the single market for telecommunications services

- Action area /Pillar 2 - Interoperability and standards …………………………………………………………………………………………………………………………………………... ………………………………………….16

- Action 2.1 Improving ICT standard-setting

- Action 2.2 Promoting better use of standards

- Action 2.3 Enhancing interoperability through coordination

- Action area /Pillar 3 - Trust and security ………………………………………………………………………………………………………………………………………………………… …………………………..19

- Action area /Pillar 4 - Fast and ultrafast internet access ...................................................................................................................................................................................................................................................................................26

- Action 4.1 Guarantee universal broadband coverage with increasing speeds

- Action 4.2 Foster the deployment of NGA networks

- Action 4.3 Open and neutral internet

- Action area /Pillar 5 - Research and innovation ……………………………………………………………………………………………………………………………………………….……………………………………. 36

- Action 5.1 Step up efforts and efficiency

- Action 5.2 Driving ICT innovation by exploiting the single market

- Action 5.3 Industry-led initiatives for open innovation

- Action area /Pillar 6 – Enhancing digital literacy, skills and inclusion ……………………………………………………………………………………………………………………….. …………………………………………………………….40

- Action 6.1 Digital literacy and skills

- Action 6.2 Inclusive digital services

- Action area /Pillar 7 - ICT-enabled benefits for EU society ………………………………………………………………………………………………………………………………………………………………………………………..45

- Action 7.1 ICT for environment

- Action 7.2 Sustainable healthcare and ICT-based support for dignified and independent living

- Action 7.3 Promoting cultural diversity and creative content

- Action 7.4 e-Government

- Action 7.5 Intelligent Transport Systems for efficient transport and better mobility

- International aspects of the Digital Agenda ……………………………………………………………………………………………………………………………………….. 59

Digital Agenda Review package . December 2012………………………………………………………………………………………………………………………………… 60

A European borderless economy – The Digital Single Market ………………………………………………………………………………………………………………….. 60

Speeding up public sector innovation …………………………………………………………………………………………………………………………………………… .. 61

Very fast internet supply and demand ……………………………………………………………………………………………………………………………………………. 62

Cloud Computing ………………………………………………………………………………………………………………………………………………………………… .. 63

Trust and Security ………………………………………………………………………………………………………………………………………………………………….. 64

- Entrepreneurship and digital jobs and skills ………………………………………………………………………………………………………………………………………64

- Beyond R&D&I: An industrial agenda for key enabling technologies ………………………………………………………………………………………………………….. 64

- Abbreviations ……………………………………………………………………………………………………………………………………………………………………….. 65

| Tasks | Scoreboard | Description | Level | Digital Agenda Deadline DD/MM/YYY |  | DAE Implementation Status | Next steps on European Commission level | DAE Implementation Status in Bulgaria | Indicators in Bulgaria |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 |
|  |  |  |  |  | (Source: Digital Agenda Scoreboard) |  |  | (Source: Institutions/Departments) |  |
| Action area /Pillar 1 – A vibrant digital single market |  |  |  |  |  |  |  |  |  |
| Action 1.1. Opening up access to content |  |  |  |  |  |  |  |  |  |
| 1 | 001 | The EC will simplify copyright clearance, management and cross-border licensing by - Enhancing the governance, transparency and pan European licensing for (online) rights management by proposing a framework Directive on collective rights management by 2010. | EC | 31/12/2010 |  | Completed Proposal for Directive on Collective Managements of Copyright and Related Rights and multi-territorial licencing adopted 11 July 2012 | Source: MC Adoption of a Directive of the European Parliament and the Council for Collective Rights Management and multi-territorial licensing rights of music online in the internal market by 31 December 2012. | Source:MC Preparation of amendments of the Law on the Copyright and Related Rights within 12 months after the adoption of the Directive by the European Parliament |  |
| 2 | 002 | The EC will simplify copyright clearance, management and cross-border licensing by - Create a legal framework to facilitate the digitalisation and dissemination of cultural works in Europe by proposing a Directive on Orphan Works by 2010, to conduct a dialogue with stakeholders with a view to further measures on out-of print works, complemented by rights information databases. | EC | 31/12/2010 |  | Completed Proposal for Directive on Orphan Works adopted 24 May 2011. MoU on out-of-print works signed on 20 September 2011. | Source: MC Expecting adoption of Directive on Orphan Works till 31 December 2012. | Source: MC The period to 31 December 2013 will include transposition of the Directive on Collective Management of Copyright and Related Rights and multi-territorial licensing rights to music online for purposes of the internal market. |  |
| 3 | 003 | The EC will simplify copyright clearance, management and cross-border licensing by - By 2012, review the Directive on Re-Use of Public Sector Information, notably its scope and principles on charging for access and use. | EC | 31/12/2012 |  | Completed Open Data Package incl. revised Directive adopted on 12 December 2011 | Various sectoral actions will apply the concept, e.g. Marine Knowledge initiative to unlock marine data into the public domain. | Source: MTITC, MC Within 12 months after its adoption at EU level. | Adopted Amendment of Access to Public Information Act (APIA) |
| 4 | 004 | The EC will after an extensive stakeholder dialogue, report by 2012 on the need for additional measures beyond collective rights management allowing EU citizens, online content services providers and right-holders to benefit from the full potential of the digital internal market, including measures to promote cross-border and pan-European licenses, without excluding or favouring at this stage any possible legal option. | EC | 31/12/2012 |  | Completed IPR strategy adopted 24 May 2011. (follow –up through Action 5) |  | Source: MC Sent letter to the collecting society, for their opinion on the text of the draft Directive on Collective Management of Copyright and Related Rights and multi-territorial licensing rights to music online for purposes of the internal market. |  |
| 5 | 005 | In preparation thereof, issue a Green Paper addressing the opportunities and challenges of online distribution of audiovisual works and other creative content by 2010. | EC | 31/12/2010 |  | Completed Green Paper adopted on 13 July 2011. | Report on consultation the Green Paper forthcoming. | Source: MC Public consultation and results in mid-2012 | Source: MC Constant monitoring from CEM (The Council for Electronic Media) and annual report of the rates to EC. |
| 6 | 006 | On the basis of the review of the Directive on the Enforcement of Intellectual Property Rights, and following extensive stakeholder dialogue, report by 2012 on the need for additional measures to reinforce the protection against persistent violations of intellectual property rights in the online environment, consistent with the guarantees provided in the Telecoms Framework and fundamental rights on data protection and privacy. | EC | 31/12/2012 |  | On track The review of the IPR Enforcement Directive is on-going and a public consultation on the civil enforcement of intellectual property rights was launched on 30 November 2012 and will stay open until 30 March 2013. |  |  |  |
| Action 1.2. Making online and cross border transactions straightforward |  |  |  |  |  |  |  |  |  |
| 7 | 007 | The EC will ensure the completion of the Single Euro Payment Area (SEPA), eventually by binding legal measures fixing an end date for migration before 2010 and facilitate the emergence of an interoperable European eInvoicing framework through a Communication on eInvoicing and by establishing a multistakeholder forum. | EC | 31/12/2012 |  | Completed Proposal for SEPA migration end-date adopted 16 December 2010, Communication on e-Invoicing adopted 2 December 2010. Green Paper on card, Internet and mobile payments adopted on 11 January 2012. |  | Source: BNB On 28 February 2012 Regulation of the European Parliament and of the Council was adopted establishing a deadline date on February 1, 2014 for the migration of the Eurozone countries to SEPA credit transfers and direct debits (for most conditions) in Euros. For Bulgaria and other EU member states outside the Eurozone date is 31 October 2016, or 1 year after the adoption of the euro (whichever occurs first). It determines the phasing out of Multilateral Interchange Fees (MIFs), which currently can be used to direct debits in some Member States, on 1 February 2017 for national payments. It also determines the phasing out, not later than 1 February 2016, the requirement to provide Business Identification Code (BIC), the only identifier for all cross-border and national payments remains IBAN. The regulation covers all transactions such as credit transfers and direct debits in Euros within the EU, but generally does not affect transactions with payment cards, money remittance, and electronic payment transactions. In terms of e-Invoicing at that time, a European multilateral forum on e-invoicing, which includes representatives from Bulgaria, supported by a group of the NSAID, working as a national forum on e-Invoicing |  |
| 8 | 009 | The EC will evaluate by end 2010 the impact of the e-Commerce Directive on online markets and make concrete proposals. | EC | 31/12/2011 |  | Completed Communication adopted on 11 January 2012. It was deemed unnecessary to revise the eCommerce Directive at this point. | Commission to provide some guidance on interpretation (notice & action). |  |  |
| 9 | 010 | Member States should implement swiftly and coherently the key Directives supporting the digital single market, including Services Directive. | BG | 31/12/2015 |  | On track |  | Source: МТIТС, MEET MTITC provides access to PSCs in SPAAS MEET is responsible for a policy directive. The Directive 2006/123/EU of the European Parliament and the Council on 12 December 2006, on the services on the internal market was initiated the national legislation by the Law on the provision of services, in force from 23 February 2010. In 2012 it was prepared a project for amendment of the Law on the Provision of Services. The project aims to specify and complement the current national regulation in the area of establishment and freedom to provide services to be in correspondence with the European regulations in the area of services in the internal market. The made proposals for amendments are with regard of recommendations of the EC, related with the necessity of legislative measures on national leval in conjunction with the apllying of Directive 2006/123/EU. These measures will establish better secutiry for services suppliers’ in Bulgaria. The Regulation is approved on a meeting of Council of Ministers (CM) of Republic of Bulgaria on 21 November 2012 with a Decision № 966/22 Noveber 2012 and will be discussed in the Bulgarian Parliament. It is expected the regulation to be accepted from the Bulgarian Parliament during the first half of 2013. In conjunction with the necessity of establishing a regulatory framework for the functioning of the Single Point for Contact (which every Member States should establish, according to Services Directive), in the regulation is foreseen the CM to accept an ordinance for the conditions of maintainance and functioning of Single Points for Contact , both proposed by the MEET and MTITC. |  |
| 10 | 010 | Member States should implement swiftly and coherently the key Directives supporting the digital single market, including Unfair Commercial Practices Directive | BG | 31/12/2015 |  | On track |  |  |  |
| 11 | 010 | Member States should implement swiftly and coherently the key Directives supporting the digital single market, including revised in 2009 of EU Rregulatory Telecoms Framework | BG | 31/12/2015 |  | On track |  | Source: МТIТС Completed | Adopted amendment to Electronic Communications Act (amend. SG. 105/29 Dec 2011) |
| 12 | 008 | In 2011 propose a revision of the eSignature Directive with a view to provide a legal framework for cross-border recognition and interoperability of secure eAuthentication systems. | EC | 31/12/2011 |  | Completed Legislative proposal adopted on 04 06 2012, coupled with eID following the Single Market Act. |  |  |  |
| 13 | 011 | Member States should transpose by 2013 the VAT Directive ensuring equal treatment for e Invoicing with paper invoices | BG | 31/12/2013 |  | On track |  | Source: MF Completed | Source: MF Adopted amendments of Value Added Tax Act (amend. SG 94/30 Nov 2012 ) Transposition of 2010/45/EC Directive |
| Action 1.3 Building digital confidence |  |  |  |  |  |  |  |  |  |
| 14 | Key action 4 | The EC will review the EU Data Protection Regulatory Framework with a view to enhancing individuals' confidence and strengthening their rights, by the end of 2010. | EC | 31/12/2010 |  | Completed Proposal adopted on 25 January 2012. | On legislative track. | Source: MTITC Part of a general framework for data protection in the EU electronic communications sector is Directive 2002/58/EC as amended by Directive 2009/136/EC. The provisions of Directive 2002/58/EC are introduced by amendments to the Electronic Communications Act adopted in late 2011. | Adopted amendment to Electronic Communications Act (amend. SG. 105/29 Dec 2011) |
| 15 | 013 | The EC will propose by 2012 an optional contract law instrument complementing the Consumer Rights Directive to overcome the fragmentation of contract law, in particular as regards the online environment | EC | 31/12/2012 |  | Completed Proposal adopted 11 October 2011. | . On legislative track |  |  |
| 16 | 014 | The EC will explore by 2011 initiatives on consumer Alternative Dispute Resolution Green paper in the EU with a view to making proposals for an EU-wide Online Dispute Resolution system for eCommerce transactions by 2012 | EC | 31/12/2012 |  | Completed Proposal for a Common European Sales Law adopted 29 November 2011. On legislative track. | On legislative track |  |  |
| 17 | 015 | The EC will explore proposals in the field of collective redress, based on stakeholder consultation. | EC | 31/12/2015 |  | On track After 2011 public consultation Commission decided it was premature to start policy intervention in this field. |  |  |  |
| 18 | 016 | The EC will issue a Code of EU Online Rights by 2012 that summarises existing digital user rights in the EU in a clear and accessible way, complemented by an annual sweep of breaches of online consumer protection law and appropriate enforcement measures, in coordination with the European Network of Consumer Protection Agencies | EC | 31/12/2012 |  | On track The Comission updates the Code of Online Rights at the end of 2012. |  |  |  |
| 19 | 017 | The EC will create a stakeholder platform by 2012 for EU online trustmarks, notably for retail websites | EC | 31/12/2012 |  | On track The Comission has conducted a study and final results are expected end of 2012. |  |  |  |
| Action 1.4 Reinforcing the single market for telecommunications services |  |  |  |  |  |  |  |  |  |
| 20 | 018 | The EC will propose measures for an increased harmonisation of numbering resources for provision of business services across Europe by 2011 | EC | 31/12/2011 |  | Completed Public consultation concluded no need for this harmonization. |  | Source: MTITC National level actions are not needed. |  |
| 21 | 019 | The EC will on the basis of the European Radio Spectrum Policy Programme, coordinate the technical and regulatory conditions applying to spectrum use and, where necessary, harmonise spectrum bands to create economies of scale in equipment markets and allow consumers to use the same equipment and avail themselves of the same services across the EU. | EC | 31/12/2010 |  | Completed Proposal adopted 20 September 2010. Legislative process concluded in 2012. |  | Source: MTITC, CRC, MD, NSP In progress. Some of the provisions of the Programme are implemented in Bulgaria. Republic of Bulgaria has transposed the EC decisions related to the use of spectrum. Not yet implemented Decision 2008/477/EC (2500-2690 MHz) and Decision 2010/267/EU (790-862 MHz) Acting on the basis of Article 1, paragraph 3 from Decision № 243/2012/ЕU of the European Parliament and the Council on 14 March 2012 for establishing a multi-annual programme for policy in the field of radiofrequency spectrum, the bulgarian side informed the EC (a letter to Mrs. Katrin Dey), that the readiofrequency band 800 MHz is being used in Republic of Bulgaria for the needs of the defence. Defined radiofrequency bands are being used for broadcasting in particular regions of the country under coordination with the Ministry of Defence. The indicated radiofrequency band will continue to be in use for the needs of the defence until the end of operation of the communication systems in use. | Released and harmonised radiofrequency bands. |
| 22 | 020 | The EC will conduct by 2011 an investigation into the cost of non-Europe in telecommunication markets to take further measures to reinforce the benefits of the single market. | EC | 31/12/2011 |  | Completed Study published on 28 February 2012. |  |  | Source MTITC: Measures taken, including possible changes in the Electronic Communications Regulatory Framework. |
| 22а | 101 | The difference in price between calls in roaming and long distance calls within a country should be close to zero no later than 2015 | EC | 31/12/2012 |  | Completed Proposal for Regulation on roaming on public mobile communications networks adopted 6 July 2011. Legislative process concluded in 2012. |  | Source: MTITC An interinstitutional Working Group established. The group has prepared the amendment of the relevant legislative provisions of Electronic Communications Act. | Source MTITC: Adopted amendment to Electronic Communications Act, introducing provisions of the new Regulation on roaming. |
| Action Area/Pillar 2 - Interoperability and standards |  |  |  |  |  |  |  |  |  |
| Action 2.1 Improving ICT standard-setting |  |  |  |  |  |  |  |  |  |
| Action 2.2 Promoting better use of standards |  |  |  |  |  |  |  |  |  |
| Action 2.3 Enhancing interoperability through coordination |  |  |  |  |  |  |  |  |  |
| 23 | 021 | The EC will as part of the review of EU standardisation policy, propose legal measures on ICT interoperability by 2010 to reform the rules on implementation of ICT standards in Europe to allow use of certain ICT fora and consortia standards | EC | 31/12/2010 |  | Completed Proposal adopted 1 June 2011. Formally completed with the adoption in December 2010 of the “Revised rules for the assessment of horizontal cooperation agreements under EU competition law”. The Council adopted on 4 October 2012 the Regulation (EU) No 1025/2012 of the European Parliament and of the Council on European standartisation. | On legislative track . |  |  |
| 24 | 022 | The EC will promote appropriate rules for essential intellectual property rights and licensing conditions in standard-setting, including for ex-ante disclosure, in particular through guidelines by 2011. | EC | 31/12/2011 |  | Completed Adopted 14 January 2011. |  |  |  |
| 25 | 026 | Member States should apply the European Interoperability Framework at national level by 2013 | BG | 31/12/2013 |  | On track |  | Source: MTITC Running processes Update of Bulgarian Interoperability Framework. Set out in the Roadmap | Updated Bulgarian Interoperability Framework. National Interoperability Strategy |
| 26 | 023 | The EC will issue a Communication in 2011 to provide guidance on the link between ICT standardisation and public procurement to help public authorities to use standards to promote efficiency and reduce lock-in. | EC | 31/12/2011 |  | Delayed | The Comission will make a proposal in the first half of 2013 |  |  |
| 27 | 027 | Member States should implement commitments on interoperability and standards in the Malmö and Granada Declarations by 2013. | BG | 31/12/2013 |  | On track The Commission is monitoring the current status of interoperability in Member states and EU administrations through the National Interoperability Framework Observatory and via yearly implementation reviews of the European Interoperability Strategy. |  | Source: MTITC Project OPAC - selection of contractor for the OP: Item 5. Improving interoperability and providing opportunities for integration at the European level; |  |
| 28 | 024 | The EC will promote interoperability by adopting in 2010 a European Interoperability Strategy and European Interoperability Framework. | EC | 31/12/2010 |  | Completed Adopted 16 December 2010. |  |  |  |
| 29 | 025 | The EC will examine the feasibility of measures that could lead significant market players to license interoperability information to report by 2012. | EC | 31/12/2012 |  | Completed Following a public consultation on Access to Interoperability Information of Digital Products and Services, no legislative action will be proposed during this mandate. Soft measures centred on best licensing practices and model licences will be further explored and developed. |  |  |  |
| Action Area /Pillar 3 - Trust and security |  |  |  |  |  |  |  |  |  |
| 30 | 028 | The EC will present in 2010 measures aiming at a reinforced and high level Network and Information Security Policy, including legislative initiatives such as a modernised European Network and Information Security Agency (ENISA), and measures allowing faster reactions in the event of cyber attacks, including a CERT for the EU institutions | EC | 31/12/2012 |  | On track On 30 September 2010 the Commission proposed a new Regulation on modernization of ENISA. | Following legislative track. |  |  |
| 31 | 030 | The EC will establish a European Cybercrime Platform by 2012 | EC | 31/12/2012 |  | On track |  |  |  |
| 32 | 031 | The EC will examine the feasibility by 2011 to create a European Cybercrime Centre. | EC | 31/12/2011 |  | Completed Communication on European Cybercrime Centre adopted on 28 March 2012. The centre to start operations in January 2013. |  |  |  |
| 33 | 032 | The EC will work with global stakeholders notably to strengthen global risk management in the digital and in the physical sphere and conduct internationally coordinated targeted actions against computer-based crime and security attacks. | EC | 31/12/2015 |  | On track EU & USA conducted readiness tests for cyber attacks in "Cyber Atlantic 2011" |  |  |  |
| 34 | 038 | Member States should establish by 2012 a well-functioning network of CERTs at national level covering all of Europe | BG | 31/12/2012 |  | On track |  | Source: EA ECNIS Center for Governmental Computer Emergency Response was established in 2008 The expansion of its functions is a continuous ongoing process The new Structural Regulations of the Executive Agency “Electronic Communication Networks and Information Systems” from April 2012, will contribute for this process. The strengthened financial and institutional capacity of the Executive Agency “Electronic Communication Networks and Information Systems” will contribute for considerable expansion of the offered reactive and pro-active services portfolio from Computer Security Incidents Response Team | Indicators are in accordance with the ENISA guidelines - "Compendium of best practices for assessing CERT" Indicators are expressed in number of services provided |
| 35 | 039 | Member States should be in cooperation with the Commission carry out large scale attack simulation and test mitigation strategies as of 2010. | BG | 31/12/2010 |  | Delayed Not all Member States have yet carried out their simulations. The first pan-European study – 04 November 2010, international teaching EU-US – 07 November 2011 conducted. |  | Source: MTITC Delayed Not started preparation and planning that lasts about 12 months. | National training for protection of Critical Information Infrastructure. |
| 36 | 029 | The EC will present measures, including legislative initiatives, to combat cyber attacks against information systems by 2010, and related rules on jurisdiction in cyberspace at European and international levels by 2013 | EC | 31/12/2010 |  | Completed Proposal for a Directive on Attacks against Information Systems adopted 30 September 2010. |  |  |  |
| 37 | 033 | The EC will support EU-wide cyber-security preparedness exercises, from 2010 | EC | 31/12/2015 |  | On track First pan-European simulation "Cyber-Europe 2010" in November 2010. |  | Source: MTITC; EA ECNIS Computer-based training “ Cyber Winter 2011” 07 December 2011 Cyber training during Regional Cyber-security Forum for the countries of South-Еastern Europe, Sofia, 28 October 2012 ili 26 October 1012 on cybersecurity and cybercrime | Number of Cyber Security Trainings done |
| 38 | 034 | EC will as part of the modernisation of the EU Personal Data Protection Regulatory Framework make it more coherent and legally certain, explore the extension of security breach notification provisions | EC | 31/12/2012 |  | Completed See Task 14. |  | Source: MTITC Running processes Part of a general framework for data protection in the EU electronic communications sector is Directive 2002/58/EC as amended by Directive 2009/136/EC. The provisions of Directive 2002/58/EC are introduced by amendments to the Electronic Communications Act adopted at the end of 2011 the European Commission is expected to provide an overview of the framework for data protection in the EU towards its modernization. | Adopted amendment to Electronic Communications Act (amend. SG. 105/29 Dec 2011) |
| 39 | 035 | The EC will give guidance by 2011 for the implementation of new Telecoms Framework with regard to the protection of individuals' privacy and personal data | EC | 31/12/2011 |  | Completed Guidance was provided to Member States on the transposition of the e Privacy Directive in October 2010. After a stock-tracking report in 2012 it was concluded that no additional guidance was needed at this stage. |  |  | Source: MTITC Adopted amendment to Electronic Communications Act (ECA) (amend. SG. 105/29 Dec 2011) Implementing Electronic Communications Act: The Commission of Personal Data Protection shall publish instructions for the circumstances under which the users shall be informed for security compromising of their personal data, the form and the way of notification. CRC is obliged to provide annually to the Commission and ENISA report notifications for breaches of security or loss of integrity. |
| 40 | 036 | The EC will support reporting points for illegal content online (hotlines) and awareness campaigns on online safety for children run at national level and enhance pan-European cooperation and sharing of best practice in this field | EC | 31/12/2015 |  | On track Communication "Strategy for a Better Internet for Children" published 2 May 2012. |  | Source: MC: Ministry of Culture actively works together with the National Safer Internet Centre | Source: MC Impementation is regular Safer Internet Public Council approved the 2012 report and outlined priorities for 2013. The new programme framework 2014-2020 adoption is comming. Safer Internet Programme is part of “Connecting Europe” Programme. 05 February 2013-International day for Safer Internet. |
| 41 | 037 | The EC will foster multi-stakeholder dialogue and self-regulation of European and global service providers (e.g. social networking platforms, mobile communications providers), especially as regards use of their services by minors. | EC | 31/12/2015 |  | On track This Task is in addition to Task 14 of this table. Coalition of top tech & media companies to make internet better place for children launched 1 December 2011. |  |  | Source:MC Actions for strengthening the dialogue undertaken. Adopted common working procedures for the Bulgarian line online safety . |
| 42 | 040 | Member States should fully implement hotlines for reporting offensive or harmful online content, organise awareness raising campaigns on online safety for children, and offer teaching online safety in schools, and encourage providers of online services to implement self-regulatory measures regarding online safety for children by 2013 | BG | 31/12/2013 |  | On track On 29 November 2011 the Council adopted conclusions on the protection of minors in digital world, which includes provisions for Member States to act in this area including teaching lessons on online safety in schools. |  |  | Source: MC Such hotline works successfully in Bulgaria from 2012. Adopted common working procedures for the Bulgarian line online safety . |
| 43 | 041 | Member States should set up or adapt National Alert Platforms to the Europol Cybercrime Platform, by 2012, starting in 2010. | BG | 31/12/2012 |  | On track Set up or adapt National Alert Platforms to the Europol Cybercrime Platform by 2012. |  |  |  |
| Action Area /Pillar 4 - Fast and ultrafast internet access |  |  |  |  |  |  |  |  |  |
| Action 4.1 Guarantee universal broadband coverage with increasing speeds |  |  |  |  |  |  |  |  |  |
| Action 4.2 Foster the deployment of NGA networks |  |  |  |  |  |  |  |  |  |
| Action 4.3 Open and neutral internet |  |  |  |  |  |  |  |  |  |
| 44 | 042 | The EC adopt in 2010 a Broadband Communication that lays out a common framework for actions at EU and Member State to meet the Europe 2020 broadband targets, including: | EC | 31/12/2010 |  | Completed |  | Source: MTITC: Completed | Adopted amendment to Electronic Communications Act (ECA) (amend. SG. 105/29 Dec 2011). Ordinance № 35 developed jointly by MTITC and the Ministry of Regional Development and Public Works on rules and regulations for the design, construction and commissioning of cable electronic communications networks |
| 44 | 043 | - Reinforce and rationalise, in this framework, the funding of high-speed broadband through EU instruments (e.g. ERDF, ERDP, EAFRD, TEN, CIP) by 2014 and - Explore how to attract capital for broadband investments through credit enhancement (backed by the EIB and EU funds). |  | 31/12/2014 |  | On track Funding for high-speed broadband is part of the 2014-2020 Cohesion Policy and the Connecting Europe Facility (CEF) |  |  |  |
| 45 | 044 | The EC adopt in 2010 a Broadband Communication that lays out a common framework for actions at EU and Member States to meet the Europe 2020 broadband targets, including: · Propose an ambitious European Spectrum Policy Programme in 2010 for decision by the European Parliament and the Council that will create a co-ordinated and strategic spectrum policy at EU level in order to increase the efficiency of radio spectrum management and maximise the benefits for consumers and industry. | EC | 31/12/2010 |  | Completed Proposal adopted 20 September 2010. Legislative process concluded in 2012. | Adopted by the European Parliament on 15 February 2012. | Source: MTITC, CRC, MD, NSP In progress. Some of the provisions of the Programme are implemented in Bulgaria. Republic of Bulgaria has transposed the EC decisions related to the use of spectrum. Not yet implemented Decision 2008/477/EC (2500-2690 MHz) and Decision 2010/267/EU (790-862 MHz) Acting on the basis of Article 1, Paragraph 3 of Decision № 243/2012/ЕU of European Parliament and the Council from 14 March 2012 for establishing Multi-annual Radiofrequency Spectrum Programme, Bulgarian side has notified EC (a letter to Mrs. Katrin Dey), that radiofrequency band 800 MHz in Bulgaria is in use for the needs of defence. | Released and harmonised radiofrequency bands. |
| 46 | 045 | The EC adopt in 2010 a Broadband Communication that lays out a common framework for actions at EU and Member State to meet the Europe 2020 broadband targets, including: - Issue a Recommendation in 2010 to encourage investment in competitive Next Generation Access networks through clear and effective regulatory measures. | EC | 31/12/2010 |  | Completed Adopted 20 September 2010. NGA Recommendation is adopted. The main objective of the Recommendation is to give guidance to NRAs on regulatory measures to undertakings with significant market impact in terms of accessibility, thereby stimulating market competition and facilitate the entry of new players. Recommendation will allow at the same time the use of unified regulatory approaches to reduce the difference in the regulation of fiber-optic networks in different MS. According to Art. 19 of the Framework Directive, NRAs must take utmost account of the provisions of the Recommendation. |  | Source: MTITC: Completed | Source: MTITC Implementation of the Recommendation from the CRC In the market analysis of markets 4 and 5 (of the EC Recommendation 2007/879/EC of 17 December 2007) obligations on access to the next generation networks are imposed for the company with significant market impact. |
| 47 | 046 | Member States should develop and make operational National Broadband Plans by 2012 that meet the coverage and speed and take-up targets defined in Europe 2020, using public financing in line with EU competition and state aid rules, the Commission will report annually on progress as part of the Digital Agenda governance. | BG | 31/12/2012 |  | On track Comission staff working document on implementation of National Broadband Plans published 30 March 2012. |  | Source: MTITC During a meeting of Council of Ministers (CM) on 19 December 2012 the updated and upgraded National Strategy for Broadband Access Development in 2015 with reference to 2020 is adopted and the National Operational Plan for the implementation of the set strategic goals. |  |
| 48 | 047 | Member States should take measures, including legal provisions, to facilitate broadband investment, such as making sure that civil engineering works systematically involve potential investors, clearing rights of way, mapping available passive infrastructure suitable for cabling and upgrading in-building wiring. | BG | 31/12/2015 |  | On track | To seek support of the MS for the adoption of legislation in the pipeline and seek effective and harmonised implementation of the adopted measures. | Source: MTITC In progress (2012-2015) The National Operational Plan provides measures and activities to coordinate the efforts of various agencies involved in the investment process in the development of broadband access in order to facilitate the process and to reduce the investment costs. Part of provisions to contribute to the implementation of this action are included in Chapter 17 of the draft amendments to the ECA, and others are in the Spatial Development Act. Member States shall take concrete measures to facilitate the implementation of infrastructure (promoting collocation, measures for sharing of infrastructure, physical infrastructure map) | Adopted amendment to Electronic Communications Act (ECA) (amend. SG. 105/29 Dec 2011). Ordinance № 35 from 30 November 2012 is published , for the rules and standards for design, construction and commissioning of cable electronic communications networks and surrounding infrastructure (amend. SG 99/14 Dec 2012) |
| 49 | 048 | Member States should use fully the Structural and Rural Development Funds that are already earmarked for investment in ICT infrastructures and services. | BG | 31/12/2013 |  | On track |  | Source: MTITC A study funded under the Technical Assistance Program of the Development of Rural Areas on 24 January 2012 examined the provision and use of Internet and electronic services in Bulgaria with a focus on rural areas. On 19 May 2012 was applied for the MA of OPRD The results of this study will assist in the preparation of the application package for applying under OPRD for financing broadband access provisioning in remote rural areas with financial resource of 20 million € Member States shall fully allocate and deploy existing Structural Funds and Funds for rural development in terms of ICT priorities (2013) Source: MAF: Currently open period of reception of applications for grant assistance under Measure 321 "Basic services for the economy and rural areas" RDP only for projects aimed at creating and improving ICT centers, which will last until 17 August 2012. |  |
| 50 | 049 | Member States should implement the European Spectrum Policy Programme, so as to ensure the co-ordinated allocation of the spectrum needed to meet the target of 100% coverage of 30 Mbps internet by 2020, and the NGA Recommendation. | BG | 31/12/2015 |  | On track European Spectrum Policy Programme was adopted in November 2011 by the Council and the European Parliament, and must shortly be implemented by Member States in order to realize the economic potential as determined in the annual growth strategy for 2011 Addressed in the Horizon 2020 proposal adopted 30 November 2011. |  | Source: MTITC In progress Bulgarian side has taken up actions regarding the recommendations of the Commission for flexible spectrum management to facilitate the spread of mobile broadband, but the release of the frequencies involved are currently servicing the needs of security and defense and future availability for civil purposes can be possible by 2015 for the reasons of need for providing and resetting equipment and financial resources for the process. |  |
| Action Area /Pillar 5 - Research and innovation |  |  |  |  |  |  |  |  |  |
| Action 5.1 Step up efforts and efficiency |  |  |  |  |  |  |  |  |  |
| Action 5.2 Driving ICT innovation by exploiting the single market |  |  |  |  |  |  |  |  |  |
| Action 5.3 Industry-led initiatives for open innovation |  |  |  |  |  |  |  |  |  |
| 51 | 050 | The EC will leverage more private investment through the strategic use of pre-commercial procurement and public-private partnerships by using structural funds for research and innovation and by maintaining a pace of 20% yearly increase of the ICT R&D budget at least for the duration of FP7 | EC | 31/12/2015 |  | On track Addressed in the Horizon 2020 proposal adopted 30 November 2011. |  |  |  |
| 52 | 051 | The EC will reinforce the coordination and pooling of resources with Member States and industry and put greater focus on demand- and user-driven partnerships in EU support to ICT research and innovation | EC | 31/12/2015 |  | On track Addressed in the Horizon 2020 proposal adopted 30 November 2011. |  |  |  |
| 53 | 052 | The EC will start in 2011 propose measures for ‘light and fast’ access to EU research funds in ICT, making them more attractive notably to SMEs and young researchers in view of a wider implementation within the revision of the EU RTD Framework. | EC | 31/12/2011 |  | Completed Addressed in the Horizon 2020 proposal adopted 30 November 2011. |  |  |  |
| 54 | 053 | The EC will ensure sufficient financial support to joint ICT research infrastructures and innovation clusters, develop further eInfrastructures and establish an EU strategy for cloud computing notably for government and science | EC | 31/12/2015 |  | On track Addressed in the Horizon 2020 proposal adopted 30 November 2011. |  | Source: MEYS and MTITC MEYS participates in the preparation and the announcement of the call for research and building up skills in scientific cloud computing . MEYS together with MTITC participate with financial resource of 50 000 euro for joint projects developed by Bulgarian researchers and their colleagues from countries that have signed the Memorandum; MEYS shall provide support and co-funding for the participation of the National Centre for Supercomputing applications in the pan-european infrastructure PRACE via the “Scientific Research” Fund. | Number of Funded projects with Bulgarian participation |
| 55 | 054 | The EC will work with stakeholders to develop a new generation of web-based applications and services, including for multilingual content and services, by supporting standards and open platforms through EU-funded programmes. | EC | 31/12/2015 |  | On track Working paper for Network Competitiveness in the EU planned for 2012 |  |  |  |
| 56 | 055 | By 2020, MS should double annual total public spending on ICT research and development spending from 5.5bn € to11bn € (which includes EU programmes), in ways that leverage an equivalent increase in private spending from 35 € billion to 70 billion € | BG | 31/12/2020 |  | On track |  | Source: MF Planning and providing funding for the tasks implementation to be within the approved maximum expenditures of those responsible for their implementation ministries. |  |
| 57 | 056 | MS should engage in Large Scale Pilots to test and develop innovative and interoperable solutions in areas of public interest that are financed by the CIP | BG | 31/12/2015 |  | On track | Over the next 12-24 months, Member States should be involved in Large-Scale Pilot Programs to test and develop innovative and interoperable solutions in areas of public interest financed by the CIP |  | Source: MTITC ICT Policy Support Programme as part of the Competitiveness and Innovation Framework Programme (CIP)/: - MTITC held six program Information days - 2 projects type A were financed with the participation of government departments and municipalities in the previous 6 program calls for proposals. - 10 projects Type B were funded with the participation of government agencies and municipalities in the previous 6 program calls for proposals |
| Action Area /Pillar 6 – Enhancing digital literacy, skills and inclusion |  |  |  |  |  |  |  |  |  |
| Action 6.1 Digital literacy and skills |  |  |  |  |  |  |  |  |  |
| Action 6.2 Inclusive digital services |  |  |  |  |  |  |  |  |  |
| 58 | 057 | The EC will propose digital literacy and competences as a priority for the European Social Fund Regulation (2014-2020); | EC | 31/12/2012 |  | Completed Proposal for a Regulation on new European Social Fund (ESF 2014-2020) adopted 6 October 2011. | On legislative track. Start of new programme expected in 2014. |  |  |
| 59 | 058 | By 2012, The EC will develop tools to identify and recognise the competences of ICT practitioners and users, linked to the European Qualifications Framework and to EUROPASS and develop a European Framework for ICT Professionalism to increase the competences and the mobility of ICT practitioners across Europe. | EC | 31/12/2012 |  | On track | The Commission will develop tools to identify and determine the competence of users and practitioners in the field of Information and Communication Technologies (ICT) |  |  |
| 60 | 059 | The EC will make digital literacy and skills a priority of the "New skills for new jobs" Flagship to be launched in 2010, including the launch of a multi-stakeholder sectoral council for ICT skills and employment to address demand and supply aspects. | EC | 31/12/2010 |  | Completed The Program adopted 23 November 2010. |  | Sources: MLSP, MEYS In progress Increasing the number of people participating in any form of lifelong learning, including priority acquisition of digital competence programs for adult education, financed from the state budget and the European Social Fund. | Number of individuals involved in training for digital competences. |
| 61 | 060 | The EC will promote a higher participation of young women and women returners in the ICT workforce through support for web-based training resources, game based eLearning and social networking. | EC | 31/12/2015 |  | On track |  | Sources: MLSP, MEYS In progress Specific deadlines and indicators can be set after the publication of two reports of the Commission on Key Competencies (2011), as well as Equality, Social Inclusion and Education (2011) |  |
| 62 | 061 | The EC will develop in 2011 an online consumer education tool on new media technologies (e.g. consumer rights on the internet, eCommerce, data protection, media literacy, social networks etc.). This tool will provide customised information and education materials for consumers, teachers and other multipliers in the 27 Member States | EC | 31/12/2011 |  | Delayed The updated Code of EU online Rights (Task 18) takes into account the latest legislatives developments. | A community educational website called "Consumer Classroom", aimed at teachers of 12-18 year-olds, is scheduled for launch in the first half of 2013. |  |  |
| 63 | 062 | The EC will propose by 2013 EU-wide indicators of digital competences and media literacy. | EC | 31/12/2013 |  | On track In 2012 to be published results of the European Survey of Schools: ICT in education, on which base indicators will be prepared. Activities for implementation of the measure can then start. |  |  |  |
| 64 | 063 | The EC will systematically evaluate accessibility in revisions of legislation undertaken under the Digital Agenda, e.g. eCommerce, eIdentity & eSignature, following the UN Convention on the Rights of Persons with Disabilities | EC | 31/12/2015 |  | On track |  |  |  |
| 65 | 064 | Based on a review of options, the EC will make proposals by 2011 that will make sure that public sector websites (and websites providing basic services to citizens) are fully accessible by 2015 | EC | 31/12/2011 |  | Completed On 3 December 2012 the European Comission adopted a proposal for a Directive on the Accessibility of the Public Sector Bodies’ Websites. |  |  |  |
| 66 | 065 | The EC will facilitate by 2012, in cooperation with Member States and relevant stakeholders, a Memorandum of Understanding on Digital Access for persons with disabilities in compliance with the UN Convention. | BG | 31/12/2012 |  | Completed MoU signed 14 September 2010. |  |  |  |
| 67 | 066 | MS should implement by 2011 long-term e-skills and digital literacy policies and promote relevant incentives for SMEs and disadvantaged groups | BG | 31/12/2011 |  | Delayed Varying progress among Member States. Gdansk Roadmap for Digital Inclusion was developed through stakeholder consultation and launched in October 2011. |  |  | Source: MLSP Number of persons from disadvantaged groups involved in training courses on digital competences. Up to date there are 2965 individuals. |
| 68 | 067 | MS should implement by 2011 the provisions on disability in the Telecoms Framework | BG | 31/12/2011 |  | On track |  | Source: MTITC Completed | Source MTITC Adopted amendment to Electronic Communications Act (ECA) (amend. SG. 105/29 Dec 2011) A draft for amending and supplementing of Ordinance № 6 of 13 March 2008 on the requirements and parameters of quality of universal service, special measures for people with disabilities and procedure for selection of undertakings providing electronic communications networks and / or services and for imposing the obligation to provide universal service is in progress. |
| 69 | 067 | MS should implement by 2011 the provisions on disability in the Audiovisual Media Services Directive. | BG | 31/12/2011 |  | On track First Report on the application of the Audiovisual Media Services Directive (AVMSD) published 7 May 2012. |  | Source: MC Transposed in national legislation | Source: MC CEM regularly monitors the implementation of the provisions of the Directive |
| 70 | 068 | MS should mainstream eLearning in National Policies for the modernisation of education and training, including in curricula, assessment of learning outcomes and the professional development of teachers and trainers | BG | - |  | On track No end date, but under constant monitoring. |  | Set in the Roadmap. The idea is MEYS and IPA to be leading institutions. | Source MEYS Approximately 60% of the teaching materials are in electronic format |
| Action Area /Pillar 7 - ICT-enabled benefits for EU society |  |  |  |  |  |  |  |  |  |
| Action 7.1 ICT for environment |  |  |  |  |  |  |  |  |  |
| 71 | 069 | The EC will assess by 2011 whether the ICT sector has complied with the timeline to adopt common measurement methodologies for the sector's own energy performance and greenhouse gas emissions and propose legal measures if appropriate. | EC | 31/12/2011 |  | Completed Key ICT companies piloted the different available methodologies and tested their coherence and compatibility and concluded that the methodologies form a coherent framework; depending on its use more detailed guidance could be required. | In 2013, the Commission will assess the need for legal measures. | Source: Directorate ESPSED MEET At this stage we have no information about the Commission's assessment of the Pilot Methodology | Not known |
| 72 | 070 | The EC will support partnerships between the ICT sector and major emitting sectors (e.g. buildings and construction, transport and logistics, energy distribution) to improve the energy efficiency and greenhouse gas emissions of these sectors by 2013. | EC | 31/12/2013 |  | Completed Commission launched the Smart Cities and Communities initiative on 10 July 2012 to facilitate integrated approaches across sectors such as buildings, transport and energy. |  | Source: Directorate ESPSED MEET MEET is developing amendments to the Energy Sector Efficiency Act (ESAE) in relation to the implementation of Directive 2010/31/EU on the Energy Performance of Buildings. | The purpose of the amendments to the Energy Sector Efficiency Act is to reduce energy consumption, improve the energy performance of buildings, promoting the construction of buildings with near-zero energy consumption. |
| 73 | 071 | The EC will assess by 2011 the potential contribution of smart grids to the decarbonisation of energy supply in Europe and define a set of minimum functionalities to promote the interoperability of Smart Grids at European level by the end of 2010 | EC | 31/12/2011 |  | Delayed Partially completed - Task force recommendation and standardization mandate issued 2011. First set of standarts by end 2012. |  | Source: Directorate ESPSED MEET Energy from Renewable Sources Act regulates the introduction of support schemes related to development of electricity transmission and distribution networks, including interconnection, intelligent networks, and the development of regulatory and storage facilities associated with the secure operation of the electricity system development of energy production from renewable sources. | Reducing carbon emissions and improve the reliability of supply of electricity. |
| 74 | 072 | In 2011 the EC will publish a Green Paper on Solid State Lighting (SSL) to explore the barriers and to put forward policy suggestions; it will in parallel support demonstration projects using the CIP. | EC | 31/12/2011 |  | Completed Green Paper: Lighting the Future adopted 15 December 2011 |  | Source: Directorate ESPSED MEET: The requirements for the energy performance of technical building systems, including: the heating, ventilation and cooling of buildings, hot water systems and lighting shall be determined in Ordinances by the Minister of Regional Development and Public Works |  |
| 75 | - 073 | - MS should agree by the end of 2011 common additional functionalities for smart meters | BG | 31/12/2011 |  | Delayed Commission presented a set of functionalities agreed by 11 Member States in October 2011. Commission Recommendation adopted in February 2012; remaining Member States to incorporate agreed functionalities in their cost-benefit analyses by end 2012. |  | Source: Directorate ESPSED MEET In the current Energy Sector Act Efficiency is written that energy traders can provide such energy service at competitive prices to ensure traceability of the energy costs of consumers replacing existing appliances (commercial metering) with intelligent systems for measurement and control. | Traceability of the cost of energy distribution companies to end users. |
| 76 | 074 | By 2012 MS should include specifications for total lifetime costs (rather than initial purchase costs) for all public procurement of lighting installations). | BG | 31/12/2012 |  | Completed Public Procurement Directive and the Green Public Procurement Criteria for lighting equipment. |  | Source: MEET In progress. By Minutes № 38 of 13 October 2011 Council of Ministers adopted a National Action Plan to promote Green Procurement for the period 2012 – 2014. One of the overall objectives of the Plan is to reduce the cost of acquisition of products and services, taking into account the entire life cycle of products. One of the activities in the Plan is to develop methodological guidelines for the award of a Green Procurement period 2012 - 2014. Instructions have been issued by the PPA and AEE (current ASED) implementing requirements for energy efficiency and energy savings in procurement for the supply of equipment and vehicles, to minimize the cost of their life. | Source ESPSE Directorate MEET Improving energy efficiency. |
| Action 7.2 Sustainable healthcare and ICT-based support for dignified and independent living |  |  |  |  |  |  |  |  |  |
| 77 | 075 | Undertake pilot actions to equip Europeans with secure online access to their medical health data by 2015 and to achieve by 2020 widespread deployment of telemedicine services | EC | 31/12/2015 |  | On track 2 pilots funded. Staff Working Paper on Legal Framework for Telemedicine planned for second half of 2012. |  |  |  |
| 78 | 076 | Propose a recommendation defining a minimum common set of patient data for interoperability of patient records to be accessed or exchanged electronically across Member States by 2012 | EC | 31/12/2012 |  | In risk of delay | eHealth Network to adopt guidelines in first half of 2013. |  |  |
| 79 | 077 | Foster EU-wide standards, interoperability testing and certification of eHealth systems by 2015 through stakeholder dialogue. | EC | 31/12/2015 |  | On track |  |  |  |
| 80 | 078 | Reinforce the AmbientAssisted Living (AAL) Joint Programme to allow older people and persons with disabilities to live independently and be active in society. | EC | 31/12/2013 |  | On track Proposal in preparation for AAL JP continuation under Horizon 2020. |  |  |  |
| Action 7.3 Promoting cultural diversity and creative content |  |  |  |  |  |  |  |  |  |
| 81 | 079 | By 2012 the EC will propose a sustainable model for financing the EU public digital library Europeana and digitalisation of content. | EC | 31/12/2012 |  | Completed Commission Recommendation on Digitalisation and Digital Preservation adopted on 27 October 2011. Europeana is part of the Connecting Europe Facility (CEF) proposal. | On legislative track. |  | Source: MC The discussions on the follow-up actions of the EC work groups about Europeana are carried on. National Expert Council on Digitalisation (www.digicult.bg) was established in Bulgaria and is holding regular meetings. |
| 82 | 080 | By 2012 the EC will propose measures following the results of the consultation on its Green Paper on "Unlocking the potential of cultural and creative industries" | EC | 31/12/2012 |  | Completed Communication “Promoting cultural and creative sector for growth and jobs in the EU” adopted 26 September 2012. |  |  |  |
| 83 | 081 | Issue by 2011 a Recommendation on Promoting digitalisation of European cinema. | EC | 31/12/2011 |  | Delayed | Proposal for a recommendation on European film in the digital era is foreseen for first half of 2013. |  |  |
| 84 | 082 | Ensure the implementation of the provisions of the Audiovisual Media Services Directive concerning cultural diversity, where appropriate through co- and self-regulation and request information from Member States on their application by the end of 2011 | EC | 31/12/2011 |  | Completed First Report on the application of the Audiovisual Media Services Directive (AVMSD) published 7 May 2012. |  | Source MC Transposed in national legislation | Source: MC Annual monitoring |
| Action 7.4 e-Government |  |  |  |  |  |  |  |  |  |
| 85 | 083 | Propose by 2012 a Council and Parliament Decision to ensure mutual recognition of e-identification and e-authentication across the EU based on online 'authentication services' to be offered in all Member States (which may use the most appropriate official citizen documents – issued by the public or the private sector) | EC | 31/12/2012 |  | Completed Legislative proposal adopted on 6 June 2012, coupled with eID following the Single Market Act. Merged with Task 12. |  | Source: MTITC Starting There is approved project within OPAC in which the system for electronic identification of Bulgarian citizens will be implemented. |  |
| 86 | 084 | The EC will support seamless cross-border eGovernment services in the Single Market through the Competitiveness and Innovation Programme (CIP) and Interoperability Solutions for European Public Administrations (ISA) Programme. | EC | 31/12/2015 |  | On track |  |  |  |
| 87 | 085 | Review by 2011 the Public access to Environmental Information Directive. | EC | 31/12/2011 |  | Delayed Communication on application of the Directive to be adopted end of 2012. |  |  |  |
| 88 | 086 | The EC will work with Member States and stakeholders to implement cross-border eEnvironment services, notably advanced sensor networks. | EC | 31/12/2015 |  | On track The priorities are outlined while the coordination and planning of the complementary actions are being improved. |  | Source: EEA On 7 March 2012 was adopted Commission Communication COM (2012) 95 final "Improving the results of the EU in the field of environment" It lays down the following targets: - establishing more effective informtion systems; - promoting the awareness and trust in the information on EU level. |  |
| 89 | 087 | Define by 2011 concrete steps in a White Paper on how to inter-connect e-Procurement capacity across the Single Market. | EC | 31/12/2011 |  | Completed Communication "Strategy for e-Procurement" published 20 April 2012. |  | Source: PPA To the end of June 2012 there is no work on projects related to the development of the system of e-Procurement by introducing the next stage of e-Procurement. | Source: PPA Currently in the EU are in progress coordination procedures to change the texts of Directives 17/2004 and 18/2004 on Public Procurement. By 2014, new requirements should be transposed into national laws of MS, and electronic data transfer is planned be compulsory to the e-offer stage in 2016. Specific actions for complete electronic communication on electronic exchange of information to e-offer stage-should be implemented in 2014 -2016 by the budget and / or the EU operational programs funding. |
| 90 | 088 | Lead by example on open and transparent eGovernment by creating in 2010 and implementing an ambitious eCommission 2011-2015 Action Plan, including full electronic procurement. | EC | 31/12/2010 |  | Completed Communication “e-Commission 2012 - 2015” adopted 1 August 2012. |  |  |  |
| 91 | 089 | MS should make e-Government services fully interoperable, overcoming organisational, technical or semantic barriers and supporting IPv6. | BG | 31/12/2015 |  | On track |  | Source MTITC Management and assets of the National Network of Public Administration (NNPA) are submitted to the Executive Agency "Electronic Communication Networks and Information Systems" (ECNIS) by the administration of Council of Ministers http://www.esmis.government.bg/page.php?c=3&d=221 |  |
| 92 | 090 | MS should ensure that the Points of Single Contact function as fully fledged e-Government centres beyond requirements and areas covered by the Services Directive. | BG | 31/12/2015 |  | On track |  | Source MTITC Announced a public tender for selection of contractor in OPAC project, which includes: "Item 4. Upgrading of the national e-Government portal to the functions of Points of Single Contact (PSC) " |  |
| 93 | 091 | MS should agree by 2011 on a common list of key cross-border public services that correspond to well defined needs – enabling entrepreneurs to set up and run a business anywhere in Europe independently of their original location, and allowing citizens to study, work, reside and retire anywhere in the European Union. These key services should be available online by 2015 | BG | 31/12/2011 |  | Delayed At Ministerial Roundtable in Poznan in November 2011, 5 key cross-border services were identified. | Agreement with Member States planned for the first half of 2013. |  |  |
| Action 7.5 Intelligent Transport Systems for efficient transport and better mobility |  |  |  |  |  |  |  |  |  |
| 94 | 092 | The EC will increase the speed of ITS take-up, in particular for road and urban transport by, applying the proposed ITS Directive in support of interoperability and rapid standardisation | EC | 31/12/2015 |  | On track |  | Source MTITC In progress On 30 November 2012 the Bularian Parliament adopted amendment on the Road Traffic Act (SG. 99/2012) which gives the CM a legal basis to adopt Ordinance on the provisions for implementing the Inteligent Transport Systems (ITS) in the road transport and for interfaces with the other types of transport (adopted on 09 January 2013 at a meeting of the CM) | Transposed Directive |
| 95 | 093 | By 2010, adopt the Air Traffic Management Solutions for the Single European Sky (SESAR) deployment strategy. | EC | 31/12/2010 |  | Completed Communication on governance and incentive mechanisms for deployment of SESAR adopted 22 September 2011. |  |  |  |
| 96 | 094 | EC will propose by 2011 a Directive for the deployment of e-Maritime services | EC | 31/12/2011 |  | Completed Directive 2010/65/EU on Reporting Formalities for Ships adopted on 29 October 2010 is an essential milestone for the use of e-Maritime services. The Commission, supported by the European Maritime Safety Agency set up an expert group gathering the different users’ administrations. |  |  |  |
| 97 | 095 | EC will propose by 2011 a Directive setting out technical specifications for telematics applications for rail passenger services | EC | 31/12/2011 |  | Completed Regulation adopted on 5 May 2011. |  |  |  |
| 98 | 096 | MS should fulfil their obligations under the European Rail Traffic Management System (ERTMS) deployment plan, in particular as regards the lines due to be equipped by 2015. | BG | 31/12/2015 |  | On track |  | Source MTITC In progress . Developed by Working Group and adopted by MTITC Minister a Strategy and National Plan of Republic of Bulgaria for ERTMS implementing | Developed and adopted a Strategy and National Plan |
| International aspects of the Digital Agenda |  |  |  |  |  |  |  |  |  |
| 99 | 097 | The EC will promote the internationalisation of internet governance and global cooperation to maintain the stability of the internet, on the basis of the multi-stakeholder model. | EC | 31/12/2015 |  | On track |  |  |  |
| 100 | 098 | The EC will support the continuation of the Internet Governance Forum beyond 2010. | EC | 31/12/2015 |  | Completed Decision at 65th UN General Assembly in December 2010, extending the IGF to 2015. |  |  |  |
| 101 | 099 | The EC will work with third countries to improve international trade conditions for digital goods and services, including with regard to intellectual property rights. | EC | 31/12/2015 |  | On track The common EU/US initiative on ICT principles was launched at the Transatlantic European Council in 2011 and is being pursued actively in the relevant WTO fora. |  |  |  |
| 102 | 100 | The EC will seek a mandate to update international agreements in line with technological progress or, where appropriate, propose new instruments. | EC | 31/12/2015 |  | On track Commission received mandate from Member States in 2009; start of technical meetings in May 2012 with a view of creating a consolidated list products for expansion of the ITA. A parallel track of non tariff barrier negotiations is under way. |  |  |  |
| Digital Agenda Review package-December 2012 |  |  |  |  |  |  |  |  |  |
| A European borderless economy – The Digital Single Market |  |  |  |  |  |  |  |  |  |
| 103 | 102 | Transformative Action: Completing the on-going review of the Copyright Framework through the preparation for legal drafting work, with a view to a decision in 2014 whether to table legislative reform proposals and seek the resolution of copyright-related issues where rapid progress is needed via a structured stakeholder dialogue in 2013. |  | 31/12/2014 |  |  |  |  |  |
| 104 | 103 | Adopt and implement the key digital single market proposals of the Digital Agenda |  | 31/12/2015 |  |  |  |  |  |
| 105 | 104 | Follow up on eCommerce Action Plan, Green Paper on payments and Consumer Agenda |  |  |  |  |  |  |  |
| 106 | 105 | Guidelines to correctly implement EU rules on consumer information requirements |  | 31/12/2014 |  |  |  |  |  |
| 107 | 106 | VAT reform - align tax rates for digital content and similar physical goods |  | 31/12/2013 |  |  |  |  |  |
| 108 | 107 | Proposals to strengthen the data industry in Europe |  | 31/12/2013 |  |  |  |  |  |
| 109 | 108 | Green paper on a converged audiovisual world |  | 31/12/2013 |  |  |  |  |  |
| Speeding up public sector innovation |  |  |  |  |  |  |  |  |  |
| 110 | 109 | Тransformative Action: Develop and implement public service infrastructures, policy and support in the framework of the Connecting Europe Facility |  | 31/12/2015 |  |  |  |  |  |
| 111 | 110 | Deploy and roll out digital services in key areas of public interest |  | 31/12/2015 |  |  |  |  |  |
| 112 | 111 | Focus and develop and implement, as appropriate the Smart Cities, Active and Healthy Ageing, Green Cars, Energy Efficient Buildings PPP |  | 31/12/2015 |  |  |  |  |  |
| Very fast internet supply and demand |  |  |  |  |  |  |  |  |  |
| 113 | 112 | Transformative Action: Durable regulatory measures on non-discrimination and wholesale pricing to promote investment and competition |  | 31/12/2014 |  |  |  |  |  |
| 114 | 113 | Recommendation on non-discrimination, first half of 2013 |  | 31/12/2013 |  |  |  |  |  |
| 115 | 114 | Recommendation on cost methodologies for regulated wholesale prices for network access, first half of 2013 |  | 31/12/2013 |  |  |  |  |  |
| 116 | 115 | Recommendation on safeguarding the open internet for consumers, first half of 2013 |  | 31/12/2013 |  |  |  |  |  |
| 117 | 116 | Update of the 2007 Recommendation on the list of markets relevant for ex ante regulation |  | 31/12/2014 |  |  |  |  |  |
| 118 | 117 | Commission Regulation on cost reductions for civil works, beginning of 2013 |  | 31/12/2013 |  |  |  |  |  |
| 119 | 118 | Update of guidelines on state aid for broadband by end 2012 |  | 31/12/2012 |  |  |  |  |  |
| 120 | 119 | Pilot project to test project bonds for broadband deployment |  | 31/12/2013 |  |  |  |  |  |
| Cloud Computing |  |  |  |  |  |  |  |  |  |
| 121 | 120 | Transformative Action: Establishment of the European Cloud Partnership to harness public buying power to accelerate the development of the market for cloud computing |  | 31/12/2013 |  |  |  |  |  |
| 122 | 121 | Follow up of the European Cloud Computing Strategy |  | 31/12/2015 |  |  |  |  |  |
| 123 | 122 | Launch pilot action to explore the efficiency gains from moving public services into the Cloud |  | 31/12/2014 |  |  |  |  |  |
| Trust and Security |  |  |  |  |  |  |  |  |  |
| 124 | 123 | Transformative Action: Directive on network and information security |  | 31/12/2013 |  |  |  |  |  |
| 125 | 124 | European Cyber Security Strategy |  | 31/12/2013 |  |  |  |  |  |
| 126 | 125 | Expand the Global Alliance against Child Sexual Abuse Online |  | 31/12/2013 |  |  |  |  |  |
| Entrepreneurship and digital jobs and skills |  |  |  |  |  |  |  |  |  |
| 127 | 126 | Transformative Action: Grand Coalition on ICT and jobs |  | 31/12/2013 |  |  |  |  |  |
| 128 | 127 | Set up a more business-friendly environment for start-ups |  | 31/12/2014 |  |  |  |  |  |
| 129 | 128 | Action Plan for web entrepreneurship |  | 31/12/2013 |  |  |  |  |  |
| Beyond R&D&I: An industrial agenda for key enabling technologies |  |  |  |  |  |  |  |  |  |
| 130 | 129 | Transformative Action: Pooling of European public and private resources for micro- and nano-electronics behind a common industrial strategy, with a strengthened Joint Undertaking at EU level as the main vector for R&D&I support. |  | 31/12/2015 |  |  |  |  |  |
| 131 | 130 | Focus and develop the photonics, robotics and Future Internet Public Private Partnership (PPP) |  | 31/12/2015 |  |  |  |  |  |
| 132 | 131 | Action plan for electronics industry in Europe, further to the 2012 strategy for Key Enabling Technologies |  | 31/12/2013 |  |  |  |  |  |
| 133 | 132 | Invest in High Performance Computing |  | 31/12/2014 |  |  |  |  |  |

December 2012

- Abbreviations

MI    	 Ministry of Interior

MF    		Ministry of Finance

MRDPW    	 Ministry of Regional Development and Public Works

MLSP		Ministry of Labour and Social Policy

MD		Ministry of Defence

MFA		Ministry of Foreign Affairs

MJ		Ministry of Justice

MEYS		Ministry of Education, Youth and Science

MH		Ministry of Health

MC		Ministry of Culture

MEW		Ministry of Environment and Water

MAF		Ministry of Agriculture and Food

MTITC	Ministry of Transport, Information Technology and Communications

MEET		Ministry of Economy, Energy and Tourism

MPES		Ministry of Physical Education and Sports

CM		Council of Ministers

MS		Member States

EC		European Commission

CRC		Communications Regulation Commission

NSI		National Statistical Institute

EA ECNIS	Executive Agency “Electronic Communication Networks & Information Systems”

BIS		Bulgarian Institute for Standardization

PPA		Public Procurement Agency

SACP		State Agency for Child Protection

CCP                    Commission for Consumer Protection

CPDP                  Commission for Personal Data Protection

PSC                     Point of Single Contact

NRIC                  National Railway Infrastructure Company

BNB                   Bulgarian National Bank

GCCA                Geodesy, Cartography and Cadastre Agency

IBA                    Invest Bulgaria Agency

NSP                    National Service for Protection

BSR                    Bulgarian State Railways

DG CAA             Directorate General Civil Aviation Administration

SPAAS 		Single portal /point of access to administrative e-services

ESPSED	Energy strategies and policies for sustainable energy development

EEA 		Executive Environment Agency

NSIC		National Safer Internet Centre

КЕТ		Key Enabling Technologies

HPC		High Performance Computing

CEM		Council of Electronic Media

EEA		Executive Environment Agency

PPA		Public Procurementr Agency