Purpose

To establish the procedure for preparation and submission of Proposal for Modification of Financing Memorandum which must be submitted by the Head of MA/IA to NC and which will be submitted to the Commission.

Background

The CF (EC Regulation 1164/94) Modification Proposal is a standard format required by the EC and it is attached as Annex E01 to the Chapter E of PIM.

Procedure

| # | Action | Function / Person responsible | Timing / Deadline | Standard Form / Template |
| --- | --- | --- | --- | --- |
|  | - PREPARATION OF THE CF 1164/94/ISPA MODIFICATION PROPOSAL |  |  |  |
|  | - Modification proposal of FM is initiated by the Tendering and contracting Department under CF, 1164/94, together with the Final Beneficiary. - In case of project implementation trough the Intermediate Body the Modification proposal of FM is initiated by the IB | Tendering and contracting Department under CF, 1164/94 or IB |  |  |
|  | - Taking into account factors such as workload and segregation of duties, assigns the task of preparation of the Modification proposal of FM to the Monitoring Department of MA/IA | MA/IA Director | - Day of receipt of information |  |
|  | - Prepares Modification proposal using standard format - Prepares Checklist – Control of CF/ISPA Modification proposal | Monitoring Expert of Monitoring Unit | - Day of receipt | - PIM – Annex E01 - Standard format : CF Modification proposal - E01 - Check-list : Control of Modification proposal |
|  | - Performs controls of the Modification proposal as assigned in the Checklist and formalises controls on the Check-list. If any problem is noticed, consult with the PIU/Engineer/IB in order to obtain further information / documents and requests any clarification | Monitoring Expert of Monitoring Unit |  | - E01 - Check-list : Control of Modification proposal |
|  | - Signs the Check-list and transmits Check-list + Modification proposal to Head of Monitoring Unit | Monitoring Expert of Monitoring Unit |  |  |
|  | - CONTROL OF THE CF 1164/94/ISPA MODIFICATION PROPOSAL |  |  |  |
|  | - Performs controls of the CF/ISPA Modification proposal as assigned in the Check list and formalises controls on the Checklist - Discuss with the Project Coordinator/IB any relevant issue | Head of Monitoring Unit | - Day of receipt of Modification proposal and Checklist |  |
|  | - Performs controls of the CF/ISPA Modification proposal as assigned in the Check list and formalises controls on the Checklist - Discuss with the Project Coordinator/IB any relevant issue | Head of Financial Control Unit |  |  |
|  | - Performs controls of the CF/ISPA Modification proposal as assigned in the Check list and formalises controls on the Checklist - Discuss with the Head of Financial Control Unit any relevant issue | Head of Payments Department |  |  |
|  | - Signs the Check-list and transmits Check-list and CF/ISPA Modification proposal to the MA/IA Director | Head of Payments Department |  |  |
|  | - APPROVAL OF THE CF 1164/94/ISPA MODIFICATION PROPOSAL |  |  |  |
|  | - Review the CF/ISPA Modification proposal and the Checklist and formalises the review on the Check list | MA/IA Director | - 2 Days of receipt CF/ISPA Modification proposal |  |
|  | - Signs the Checklist to the CF/ISPA Modification proposal | MA/IA Director |  |  |
|  | - Signs the Check-list and transmits Check-list and CF/ISPA Modification proposal to the Head of MA for approval |  |  |  |
|  | - APPROVAL OF THE CF 1164/94/ISPA MODIFICATION PROPOSAL |  |  |  |
|  | - Approve the CF/ISPA Modification proposal and the Checklist and formalises the approval on the Check list | Head of MA | - Day of receipt CF/ISPA Modification proposal |  |
|  | - Transmits Checklist and CF/ISPA Modification proposal to Monitoring Expert |  |  |  |
|  | - TRANSMISSION OF THE CF 1164/94/ISPA MODIFICATION PROPOSAL |  |  |  |
|  | - Ensures the transmission of the CF/ISPA Modification proposal to NC services and PA | Monitoring expert of Monitoring Unit | - Upon receipt of Modification proposal |  |
|  | - Files a copy of the CF/ISPA Modification proposal and Checklist | Monitoring expert of Monitoring Unit |  | - PIM - Chapter K |
|  | - COMMENTS OF THE CF 1164/94/ISPA MODIFICATION PROPOSAL |  |  |  |
|  | - Receives comments (if any) from the NC services and PA | Monitoring expert of Monitoring Unit |  |  |
|  | - Ensures the modification of the CF/ISPA Modification proposal until finalisation by applying procedure starting from point 1.4 | Monitoring expert of Monitoring Unit | - Day of receipt of comments |  |
|  | - Ensures the transmission of the final version of the CF/ISPA Modification proposal | Head of Monitoring Unit |  |  |

| Name of project: | Insert as relevant |
| --- | --- |
| FM reference N°: | Insert as relevant signed on : Insert as relevant |

HOW TO USE THE CHECK-LIST : - The boxes  represent mandatory checks to be performed. - All persons assigned to perform controls must, for each control, tick the boxes in the column corresponding to their respective position. - Comments/notes may be added on the last page of the Check-list and must be cross-referenced (numbered) in the column “Note Ref.“ - The check-list must be signed by the performers of controls and reviewers once all controls are performed

Stage 1 Preparation and First control by : Insert as relevant

Preparation started on : Date : __ / __ / ___ at __ : __

| Control # | Items to be checked | Preparation and 1st control | 2nd control | 3th control | Supervision | Supervision |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Monitoring expert | Head of Monitoring Unit | Head of Financial Control Unit | Head of Payments Dept | MA Director | Note Ref. |
|  | General format |  |  |  |  |  |  |
|  | - The format of Modification Proposal is in line with the applicable standard format | -  | -  |  |  |  |  |
|  | Measure identification |  |  |  |  |  |  |
|  | - Check : - Name of the Measure - Body Responsible - FM Reference - Rate of CF/ISPA Assistance - Dates of signature of CF/ISPA FM | -  -  -  -  -  -  | -  | -  -  -  -  -  -  | -  |  |  |
|  | - Is there any Amendment to the CF/ISPA FM ? - If so : information on Amendment number and dates of signatures are reported and are correct | -  | -  |  |  |  |  |
|  | Change of completion date |  |  |  |  |  |  |
|  | - Information on the current completion date and proposed date are complete and correct - Reconcile the current completion date with the initial FM | -  | -  |  |  |  |  |
|  | Proposed changes to the Financial plan |  |  |  |  |  |  |
|  | - Total eligible expenditures are reconciled with the current FM | -  |  | -  | -  |  |  |
|  | - Eligible expenditure spent (or expenditure forecast) are reconciled with the data in the Expenditure plan in the last Monthly Progress Sheet and the figures in the last Monthly Financial Report of the MA/IA. | -  |  | -  | -  |  |  |
|  | Changes in eligible measure costs |  |  |  |  |  |  |
|  | - The information for current total eligible cost is reconciled with the signed FM. | -  |  | -  | -  |  |  |
|  | - Change requested is checked as result of difference between current total eligible cost and proposed eligible cost. | -  |  | -  |  |  |  |
|  | Changes in physical indicators |  |  |  |  |  |  |
|  | - Current estimate to completion of physical indicators is reconciled with the last Monthly Progress Sheet. | -  | -  |  |  |  |  |
|  | Changes in the characteristics of the measure |  |  |  |  |  |  |
|  | - Changes in the characteristics of the measure are well described | -  | -  | -  | -  |  |  |
|  | Reasons for proposed changes |  |  |  |  |  |  |
|  | - The reasons for proposed changes are justified in details. - Supporting documents attached, if necessary | -  | -  | -  | -  |  |  |
|  | Modified Financial Plan |  |  |  |  |  |  |
|  | - Modified Financial Plan attached | -  |  | -  |  |  |  |

|  | Transmission to Second Control Name / Monitoring Expert / Signature Date: Hour : : . |
| --- | --- |

| Stage 2 Second control by : Head of Monitoring Unit |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |
|  | # Controls started on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | Transmission to Third Control Name / Head of Monitoring Unit / Signature Date: Hour : : . Approved by:  Name/Head of Monitoring Department /Signature: |
| --- | --- |

| Stage 3 Third control by : Head of Financial Control Unit |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |
|  | # Controls started on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | Transmission to Supervision Name / Head of Financial Control Unit/ Signature: Date: Hour : : . |
| --- | --- |

| Stage 4 Supervision by : Head of Payments Department |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |
|  | # Controls started on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | Transmission to Supervision Name / Head of Payments Department Signature: Date: Hour : : . |
| --- | --- |

| Stage 5 Supervision : Director CPPD |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | Transmission for Approval Name / Director of MA – CPP Directorate Signature: Date: Hour : : . |
| --- | --- |

| Stage 5 Approval by : Head of Managing Authority under CF 1164/94 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | Approval : Name / Head of MA Signature: . Date: Hour : : . |
| --- | --- |

NOTES / COMMENTS / INSTRUCTIONS :

| Insert as relevant | Insert as relevant |
| --- | --- |
| Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : | Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : |
| Insert as relevant | Insert as relevant |
| Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : | Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : |
| Insert as relevant | Head of MA |
| Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : | Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : |

| INTERNAL AUDIT : This area is dedicated to comments / notes / references / etc…. of internal auditors |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ref | Date | Name | Comments | Signature |