Purpose

To establish the procedure for preparation and submission of the CF (CR 1164/94)/ISPA Monthly Progress Sheet which must be submitted by the Head of MA to NC and Head of PA/NF for discussion during Monthly Progress Meeting.

Background

The CF (CR 1164/94)/ISPA Monthly Progress Sheets provide for information about the status of each ISPA FM down to the bottom level of each contract (e.g. how the individual contracts are implemented, progress achieved, problems encountered, etc).

Procedure

| # | Action | Function / Person responsible | Timing / Deadline | Standard Form / Template |
| --- | --- | --- | --- | --- |
|  | - PREPARATION OF THE MONTHLY PROGRESS SHEET |  |  |  |
|  | - Inform the MA and the IB on the date of the next Monthly Progress Meeting | NC Services |  |  |
|  | - Taking into account factors such as workload and segregation of duties, assigns the task of preparation of the Monthly Progress Sheet to the Head of respective PIU | Head of Monitoring Unit of MA | - Day of receipt of information on date of the next Monthly Progress Meeting |  |
|  | - For each ISPA FM assigned to him/her, prepares : - - A Monthly Progress Sheet using standard format - - A Checklist – Control of Monthly Progress Sheet | Project Coordinator of PIU | - Day of receipt of request for preparation of the Monthly Monitoring Sheet | - G02 - 01 - Standard format : monthly Progress Sheet |
|  | - Head of PIU transmits the Monthly Progress Sheet to the MA | Head of PIU |  |  |
|  | - Taking into account factors such as workload and segregation of duties, assigns the task of preparation of the Monthly Progress Sheet | Head of IB | - Day of receipt of information on date of the next Monthly Progress Meeting | - IB’s Manual |
|  | - For each ISPA FM assigned to the IB (road projects), should be prepared: - - A Monthly Progress Sheet using standard format - - A Checklist – Control of Monthly Progress Sheet | Expert within the IB appointed by the Head of IB /PIU | - Day of receipt of information on date of the next Monthly Progress Meeting | - IB’s Manual |
|  | - Performs controls of the Monthly Progress Sheet as assigned in the Checklist and formalises controls on the Checklist. If any problem is noticed, consult with the PIU, Engineer and/or Contractor in order to obtain further information / documents and requests any clarification | Expert within the IB appointed by the Head of IB |  | - IB’s Manual |
|  | - Head of IB transmits the Monthly Progress Sheets to the MA | Head of IB | - Six days before the monthly meeting |  |
|  | - The CF (CR 1164/94)/ISPA Monthly Progress Sheets prepared and submitted by the IB are following the standard procedure of the MA. - For each road CF/ISPA FM assigned to him/her, he/she received a CF/ISPA Monthly Progress Sheet prepared by the Intermediate body and starts with the preparation a Checklist – Control of CF/ISPA Monthly Progress Sheet, as a first control. - In case that the controlling process identifies some problems, the MA produced comments to the CF/ISPA Monthly Progress Sheets to the IB through the ISPA MIS. - The IB makes adjustments of the CF/ISPA Monthly Progress Sheets as relevant and transmits the revised version to the MA through the ISPA MIS. | Monitoring Expert of Monitoring Unit within the MA |  | - G02 - 02 - Check-list : Control of Monthly Progress Sheet |
|  | - Performs controls of the Monthly Progress Sheet as assigned in the Checklist and formalises controls on the Checklist. If any problem is noticed, consult with the IB staff, PIU, Engineer and/or Contractor in order to obtain further information / documents and requests any clarification | Monitoring Expert of Monitoring Unit of MA |  | - G02 - 01 - Standard format : monthly Progress Sheet - G02 - 02 - Check-list : Control of Monthly Progress Sheet |
|  | - In case of irregularities, initiates relevant procedures | Project Coordinator from Tendering and Contracting for CF 1164/94 Department of MA |  | - PIM - Chapter J - Irregularities |
|  | - Signs the Check-list and transmits Check-list + Monthly Progress Sheet to Head of Monitoring Unit> - Transmits the Monthly Progress Sheet to the Financial Manager for checking the financial data (Expenditure Plan table and Advanced Information sheet for Physical and Financial Execution) | Monitoring Expert of Monitoring Unit of MA |  | - G02 - 01 - Standard format : Monthly Progress Sheet - G02 - 02 - Check-list : Control of Monthly Progress Sheet |
|  | - CONTROL OF THE MONTHLY PROGRESS SHEET |  |  |  |
|  | - Performs controls of the Monthly Progress Sheet - as assigned in the Checklist and formalises controls on the Checklist - Discuss with the Project Coordinator any relevant issue | Head of Monitoring Unit | - Day of receipt of Monthly Progress Report and Checklist |  |
|  | - In case of irregularities, initiates relevant procedures | Head of Tendering and Contracting for CF 1164/94 Department |  | - PIM - Chapter J - Irregularities |
|  | - Signs the Checklist and transmits Checklist and Monthly Progress Sheet to the Director of Coordination of Programmes and Projects Directorate | Head of Monitoring Unit |  | - G02 - 01 - Standard format : Monthly Progress Sheet - G02 - 02 - Check-list : Control of Monthly Progress |
|  | - APPROVAL OF THE MONTHLY PROGRESS SHEET |  |  |  |
|  | - Review the Monthly Progress Sheet and the Check list and formalises the review / approval on the Checklist | MA Director | - Day of receipt of Monthly Progress Sheet and the Checklist | - G02 - 01 - Standard format : Monthly Progress Sheet - G02 - 02 - Check-list : Control of Monthly Progress |
|  | - In case of irregularities, initiates relevant procedures | MA Director |  | - PIM - Chapter J - Irregularities |
|  | - Signs the Checklist to Monthly Progress Sheet | MA Director |  |  |
|  | - Transmits Checklist and Monthly Progress Sheet to the Project Coordinator of Monitoring Department of MA | MA Director |  |  |
|  | - TRANSMISSION OF THE MONTHLY PROGRESS SHEET |  |  |  |
|  | - Ensures the transmission of the Monthly Progress Sheet : - Electronic version to the NC and PA/NF through the CF/ISPA MIS - Submits signed copy of the Monthly Progress Sheet to the NF | Monitoring expert of Monitoring Unit t of MA | - 3 WD before the Monthly Meeting |  |
|  | - Files a copy of the Monthly Progress Sheet and Checklist | Monitoring expert of Monitoring Unit of MA |  | - PIM - Chapter K |
|  | - COMMENTS OF THE MONTHLY PROGRESS SHEET |  |  |  |
|  | - Receives comments (if any) from the NC services and PA/NF via MIS | Monitoring expert of Monitoring Unit of MA |  |  |
|  | - Ensures the modification of the Monthly Progress Sheet until finalisation by applying procedure starting from point 1.2 | Monitoring expert of Monitoring Unit of MA | - Day of receipt of comments |  |
|  | - Ensures that the MA and IB will be represented at the Monthly progress Meeting | Head of Monitoring Unit |  |  |
|  | - ATTENDANCE TO THE MONTHLY PROGRESS MEETING |  |  |  |
|  | - Taking into account factors such as workload and segregation of duties, assigns the task of attending the Monthly Progress Meeting to PIU, Project Coordinator of MA and Head of Monitoring Department | Director of MA |  |  |
|  | - Taking into account factors such as workload and segregation of duties, assigns the task of attending the Monthly Progress Meeting to IB staff, PIU and Project Coordinator | Head of IB |  |  |
|  | - Attends the Monthly Progress Meeting - Provides the MA management with any relevant feed-back on the Monthly Progress Meeting | Monitoring expert of MA/IA, Head of Monitoring Unit, Head of the Monitoring department, Head of Tendering and Contracting under CF 1164/94, Head of PIU, Project Coordinator of PIU | - Day of Monthly Progress Meeting |  |
|  | - Receives the minutes via MIS of the Monthly Progress Meetings from the NC services | Monitoring expert of MA | - 7 WD after the Monthly Progress Meeting |  |
|  | - Ensures the follow-up of any relevant action assigned to the IB | Head of IB |  |  |
|  | - Ensures the follow-up of any relevant action assigned to the MA | Head of Monitoring Unit |  |  |
|  | - Ensure the filing of the minutes and any related documentation | Monitoring Expert of MA |  | - PIM - Chapter K |

- CF/ISPA MONTHLY PROGRESS sheet

- cut off date:

- 1A. PROJECT Identification

Name of project: CF/ISPA Financing Memorandum reference N°: MA/Implementing Agency: Rate of CF/ISPA assistance: Signature of Financing Memorandum- Commission - Country Amendment number - Commission - Country

- 1B. Managing Authority (MA)/Implementing Agency (IA)

Name: Address: Post Code: Town: Contact Name: Telephone No.: E-mail:

- 2. Brief chronological description of activities / works carried out

- 3. Specific conditions related to the Measure (Article 8 of Financing Memorandum)

- 4.	Update of Procurement Plan

| Contract (N°, Type & Description)* |  | Date of publication of tender forecast | Type of tender envisaged** | Date of publication of tender notice |  | Cost of contract /estimated cost of contract | Type of co-financing | Date of Signature and name of the company awarded/ State of Play |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | If not published | If published | € Million | Joint/ parallel |  |
|  |  |  |  | Estimated Date | Date, OJ Ref and Internet. |  |  |  |
| Signed |  |  |  |  |  |  |  |  |
| Under preparation |  |  |  |  |  |  |  |  |

(*)	Specify the main contract.

(**)	Indicate whether the contract agreement will be either Red, Yellow or Silver book.  Specify if it is a local, international or restricted tender and give justification for procedure in case of pre-qualification

(***)	Date of sending of the Request for Services

5. ADVANCED INFORMATION SHEET FOR PHYSICAL & FINANCIAL EXECUTION STATUS cut off date

| № | Categories of eligible expenditure i.e. main components | Physical indicators (*) |  |  | Physical execution since last report | Physical execution up to this monitoring progress report | Rate of physical execution % |  | Expenditure since last monitoring committee meeting (€) | Expenditure up to this monitoring committee meeting (€) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Unit |  | Quantity |  |  |  |  |  |  |
|  |  |  |  | (1) | (2) | (3) | (4)=(3)/(1)*(%) |  | (7) | (8) |
| I. TA for Tender Evaluation |  |  |  |  |  |  |  |  |  |  |
| II. CONSTRUCTION CONTRACT ADVANCE PAYMENT |  |  |  |  |  |  |  |  |  |  |
| 1 | GENERAL ITEMS | % |  |  |  |  |  |  |  |  |
| 2 |  | m3 |  |  |  |  |  |  |  |  |
| 3 |  | m3 |  |  |  |  |  |  |  |  |
| 4 |  | m3 |  |  |  |  |  |  |  |  |
| 5 |  | kg |  |  |  |  |  |  |  |  |
| 12 | Provisional payment |  |  |  |  |  |  |  |  |  |
|  | SUB TOTAL |  |  |  |  |  |  |  |  |  |
|  | General Contingency |  |  |  |  |  |  |  |  |  |
|  | TOTAL |  |  |  |  |  |  |  |  |  |
|  | DISCOUNT |  |  |  |  |  |  |  |  |  |
|  | VALUE AFTER DISCOUNT |  |  |  |  |  |  |  |  |  |
|  | LESS RETENTION % |  |  |  |  |  |  |  |  |  |
|  | LESS ADVANCE PAYMENT % |  |  |  |  |  |  |  |  |  |
|  | PAYMENT FOR WORKS |  |  |  |  |  |  |  |  |  |
|  | TENDER TOTAL |  |  |  |  |  |  |  | 84 |  |

- 6. Reasons for differences (if any) between physical and financial execution Explanations for delays (if appropriate)

- 7. Technical, financial or legal problems (Annex III.1 of FM)

- 8. Observations and Recommendations of National and/or Community inspection authorities (Annex III.1 of FM)

- 9. Measures adopted to advertise Community Assistance (Annex III.6 of FM)

Billboards erected at the site? Yes No Media used to inform the public of the measure in hand: Press Television Radio Other audio-visual media Type of written documentation made available to the public:

- 10. Expected completion date

In initial FM (end date fixed in the initial FM) In Current FM (end date in modified FM) Expected completion date Modification of date to be proposed at MC: Yes No

| Name of measure: | Insert as relevant |
| --- | --- |
| CF/ISPA FM reference N°: | Insert as relevant signed on : Insert as relevant |

HOW TO USE THE CHECK-LIST : - The boxes  represent mandatory checks to be performed. - All persons assigned to perform controls must, for each control, tick the boxes in the column corresponding to their respective position. - Comments/notes may be added on the last page of the Check-list and must be cross-referenced (numbered) in the column “Note Ref.“ - The check-list must be signed by the performers of controls and reviewers once all controls are performed - The check-list must be used as follows: - In case of the projects implemented by the Ministry of Transport the check-list use the option “Preparation” below; - In case of the projects implemented by the Intermediate body (road projects) the check-list use the option “First control” below.

Stage 1 Preparation and First control by: Monitoring Expert of Monitoring Unit

Preparation/First control started on : Date : __ / __ / ___ at __ : __

| Control # | Items to be checked | Preparation/1st control | 2nd control | Supervision / Approval |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Monitoring expert of Monitoring Unit | Head of Monitoring Unit | MA/IA Director | Note Ref. |
|  | General format |  |  |  |  |
|  | - The format of CF/ISPA Monthly Progress Sheet is in line with the applicable standard format | -  | -  |  |  |
|  | - Cut-off date is mentioned and corresponds to the actual reporting period | -  | -  |  |  |
|  | 1a – Measure identification |  |  |  |  |
|  | - Check : - Name of the Measure - FM Reference - Rate of CF/ISPA Assistance - Dates of signature of CF/ISPA FM | -  | -  |  |  |
|  | - Is there any Amendment to the CF/ISPA FM ? - If so : information on Amendment number and dates of signatures are reported and are correct | -  | -  |  |  |
|  | 1b – Implementing Agency |  |  |  |  |
|  | - Information on the Managing Authority/Implementing Agency is complete and correct | -  | -  |  |  |
|  | 2 – Chronological description of activities / works carried out |  |  |  |  |
|  | - Activities/works carried out are properly described and take into account all relevant information up to cut-off date - Check also evolution since the previous Monthly Progress Sheet | -  | -  |  |  |
|  | 3 – Specific conditions related to the Measure (Article 8 of CF/ISPA FM) |  |  |  |  |
|  | - Reconcile the information with the CF/ISPA FM : status of the conditions are properly described and take into account all relevant information up to cut-off date - Check also evolution since the previous Monthly Progress Sheet | -  | -  |  |  |
|  | 4 – Up date of Procurement Plan |  |  |  |  |
|  | - The procurement plan is reconciled with the Internal detailed Procurement Plan of the CF/ISPA MA/IA - Check also evolution since the previous Monthly Progress Sheet | -  | -  |  |  |
|  | 6. Advanced Information sheet for Physical & Financial Execution – checked by the Project coordinator and Financial Manager |  |  |  |  |
|  | - The Advanced Information Sheet is reconciled with the Engineers progress report. - Check also evolution since the previous Monthly Progress Sheet | -  | -  |  |  |
|  | 7. – Reasons for differences (if any) between physical and Financial Execution (Explanation for delays) |  |  |  |  |
|  | - and |  |  |  |  |
|  | 8. – Technical, Financial or Legal problems (Annex III.1 of FM) |  |  |  |  |
|  | - and |  |  |  |  |
|  | 9. – Observations and recommendations of national and/or Community inspection authorities |  |  |  |  |
|  | - Check evolution since the previous Monthly Progress Sheet - Reconcile the information with any recent Audit Report in relation to the Measure under report - References (dates / reference number / audit institution) of the Audit reports must be reported here : - ………………………………………………….. | -  | -  |  |  |
|  | 10. – Measures adopted to advertise Community Assistance(Annex III.6 of CF/ISPA FM) |  |  |  |  |
|  | - Measures related to publicity are properly described and take into account all relevant information up to cut-off date - Check also evolution since the previous Monthly Progress Sheet | -  | -  |  |  |
|  | 11. – Expected completion date |  |  |  |  |
|  | - Reconcile the dates with : - Initial FM - Amendment to FM - Previous Monthly Progress Sheet - Information provided under headings: - 5 – Reasons for differences (if any) between physical and Financial Execution (Explanation for delays) - and - 6 – Technical, Financial or Legal problems (Annex III.1 of FM) | -  | -  |  |  |

| 26 | Supervision performed |  |  |  |
| --- | --- | --- | --- | --- |

|  | Transmission to Second Control Name / Monitoring Expert from Monitoring Unit of MA/IA Signature: Date: Hour : : . |
| --- | --- |

| Stage 2 Second control by : Head of Monitoring Unit |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |
|  | # Controls started on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | - Performs controls as assigned in column “Second control” |  | -  |  |  |
| --- | --- | --- | --- | --- | --- |

|  | Transmission to Supervision / Approval Name/Head of Monitoring Unit/Signature: Date: Hour : : . |
| --- | --- |

| Stage 3 Supervision / Approval by : Director CPP Directorate |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | - Review performed as assigned in column “Supervision” |  |  | -  |  |
| --- | --- | --- | --- | --- | --- |

|  | Approval: Name/Director of CPP Directorate/Signature: Date: Hour : : . |
| --- | --- |

NOTES / COMMENTS / INSTRUCTIONS :

| Insert as relevant | Insert as relevant |
| --- | --- |
| Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : | Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : |
| Insert as relevant | Insert as relevant |
| Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : | Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : |
| Insert as relevant | Head of MA/IA |
| Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : | Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : |

| INTERNAL AUDIT : This area is dedicated to comments / notes / references / etc…. of internal auditors |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ref | Date | Name | Comments | Signature |