Purpose

To establish the procedure for preparation and submission of the CF (CR 1164/94)/ISPA Monitoring Sheet which must be submitted by the Head of MA  to NC and Head of PA/NF and which will support the discussions of the CF (CR 1164/94) Monitoring Committee.

Background

The CF (CR 1164/94)/ISPA Monitoring Sheets are a standard report required by the EC to be submitted to the CF (CR 1164/94) Monitoring Committee twice a year.

Procedure

| # | Action | Function / Person responsible | Timing / Deadline | Standard Form / Template |
| --- | --- | --- | --- | --- |
|  | - PREPARATION OF THE CF (CR 1164/94)/ISPA MONITORING SHEET |  |  |  |
|  | - Inform the Head of MA on the date of the next CF (CR 1164/94) Monitoring Committee meeting; - Request the Head of MA and Head of IB to start the preparation of the Monitoring Sheet; - Specify the deadline for receiving the CF (CR 1164/94/ISPA Monitoring Sheets to be prepared by the MA | NC Services | - Information letter with the timetable for organization of CF (CR 1164/94) Monitoring Committee, prepared by NC (10th WD of the month preceding the month during which the CF/ISPA Monitoring Meeting is scheduled) |  |
|  | - Transmits to the management of the MA the instructions of the NIC service | Head of MA | - Day of receipt of information |  |
|  | - Taking into account factors such as workload and segregation of duties, assigns the task of preparation of the Monitoring Sheet to the Monitoring Department of MA | MA Director | - Day of receipt of information |  |
|  | - For each ISPA FM assigned to him/her, prepares : - - An CF (CR 1164/94)/ISPA Monitoring Sheet using standard format - - A Checklist – Control of CF (CR 1164/94)/ISPA Monitoring Sheet | Monitoring Expert of Monitoring Unit | - Day of receipt of information | - G03 - 01 - Standard format : CF/ISPA Monitoring Sheet - G03 - 02 - Check-list : Control of CF/ISPA Monitoring |
|  | - Taking into account factors such as workload and segregation of duties, assigns the task of preparation of the Monitoring Sheet | Head of IB | - Day of receipt of information |  |
|  | - For each ISPA FM assigned to the IB (road projects), should be prepared: - - An CF (CR 1164/94)/ISPA Monitoring Sheet using standard format - - A Checklist – Control of CF (CR 1164/94)/ISPA Monitoring Sheet | Expert within the IB appointed by the Head of IB /PIU | - Day of receipt of information | - IB’s Manual |
|  | - Performs controls of the Monitoring Sheet as assigned in the Checklist and formalises controls on the Check-list. If any problem is noticed, consult with the PIU/Engineer/Contractor in order to obtain further information / documents and requests any clarification | Expert within the IB appointed by the Head of IB |  | - IB’s Manual |
|  | - Head of IB transmits the CF (CR 1164/94/ISPA Monitoring Sheets to the MA | Head of IB | - 5 days prior to deadline determinate with the timetable for organization of CF (CR 1164/94) Monitoring Committee, prepared by NC (usually no later than 25 days before the respective meeting) |  |
|  | - The CF (CR 1164/94)/ISPA Monitoring Sheets prepared and submitted by the IB are following the standard control procedure of the MA. - For each road CF/ISPA FM assigned to him/her, he/she received a CF/ISPA Monitoring Sheet prepared by the Intermediate body and starts with the preparation a Checklist – Control of CF/ISPA Monitoring Sheet, as a first control. - In case that the controlling process identifies some problems, the MA produced comments to the CF/ISPA Monitoring Sheets to the IB through the ISPA MIS. - The IB makes adjustments of the CF/ISPA Monitoring Sheets as relevant and transmits the revised version to the MA through the ISPA MIS. | Monitoring Expert of Monitoring Unit |  | - G03 - 02 - Check-list : Control of CF/ISPA Monitoring |
|  | - Performs controls of the Monitoring Sheet as assigned in the Checklist and formalises controls on the Check-list. If any problem is noticed, consult with the IB staff, PIU/Engineer/Contractor in order to obtain further information / documents and requests any clarification | Monitoring Expert of Monitoring Unit |  | - G03 - 02 - Check-list : Control of CF/ISPA Monitoring Sheet |
|  | - In case of irregularities, initiates relevant procedures | Project Coordinator of Tendering and Contracting under CF 1164/94 Department |  | - PIM - Chapter J - Irregularities |
|  | - Signs the Check-list and transmits Check-list + Monitoring Sheet to Head of Monitoring Unit | Monitoring Expert of Monitoring Unit |  |  |
|  | - CONTROL OF THE MONITORING SHEET |  |  |  |
|  | - Performs controls of the Monitoring Sheet as assigned in the Check list and formalises controls on the Checklist - Discuss with the Project Coordinator any relevant issue | Head of Monitoring Unit | - Day of receipt of Monitoring Sheet and Checklist |  |
|  | - Performs controls of the Monitoring Sheet as assigned in the Check list and formalises controls on the Checklist - Discuss with the Project Coordinator any relevant issue | Head of Financial Control Unit |  |  |
|  | - Performs controls of the Monitoring Sheet as assigned in the Check list and formalises controls on the Checklist - Discuss with the Head of Financial Control Unit any relevant issue | Head of Payments Department |  |  |
|  | - In case of irregularities, initiates relevant procedures | Head of Tendering and Contracting under CF 1164/94 Department |  | - PIM - Chapter J - Irregularities |
|  | - Signs the Check-list and transmits Check-list Monitoring Sheet to the MA/IA Director | Head of Monitoring Unit |  |  |
|  | - APPROVAL OF THE MONITORING SHEET |  |  |  |
|  | - Review the Monitoring Sheet and the Checklist and formalises the review / approval on the Check list | MA Director | - Day of receipt Monitoring Sheet and Checklist |  |
|  | - In case of irregularities, initiates relevant procedures | MA Director |  | - PIM - Chapter J - Irregularities |
|  | - Signs the Checklist to the Monitoring Sheet | MA Director |  |  |
|  | - Transmits Checklist and Monitoring Sheet to Project Coordinator |  |  |  |
|  | - TRANSMISSION OF THE MONITORING SHEET |  |  |  |
|  | - Ensures the transmission of the Monitoring Sheet: - Electronic version to the NC and PA/NF through the CF/ISPA MIS | Monitoring expert of Monitoring Unit | - Upon deadline specified by the NC services in the invitation to Head of MA to prepare the Monitoring Sheet |  |
|  | - Files a copy of the Monitoring Sheet and Checklist | Monitoring expert of Monitoring Unit |  | - PIM - Chapter K |
|  | - COMMENTS OF THE MONITORING SHEET |  |  |  |
|  | - Receives comments (if any) from the NC services and PA/NF via MIS | Monitoring expert of Monitoring Unit |  |  |
|  | - Ensures the modification of the Monitoring Sheet until finalisation by applying procedure starting from point 1.2 | Monitoring expert of Monitoring Unit | - Day of receipt of comments |  |
|  | - Ensures that the Cover Page to final version of the Monitoring Sheets is signed and send to MF in time. | MA Director |  |  |
|  | - Ensures the transmission of the final version of the Monitoring Sheet: - Electronic version to the NC and PA/NF through the CF/ISPA MIS - Original hard copy to the NC services - One hard copy to the PA/NF | Head of Monitoring Unit |  |  |
|  | - ATTENDANCE TO THE MONITORING MEETING |  |  |  |
|  | - Ensures : - Transmission of the Monitoring Sheets to the CF (CR 1164/94) Monitoring Committee members - Organisation of the CF (CR 1164/94) Monitoring Committee meeting | NC Services | - 15 WD before the date scheduled for meeting of the CF (CR 1164/94) Monitoring Committee |  |
|  | - Attends the CF (CR 1164/94) Monitoring Committee | Head of MA (or his/her duly appointed representative) Head of IB (or his/her duly appointed representative) | - Day of meeting of the CF (CR 1164/94) Monitoring Committee |  |
|  | - Receives the minutes of the Monitoring Meeting from the NC services | MA Director Head of IB | - 14 WD after the Monitoring Meeting |  |
|  | - Instructs the MA for follow-up of any relevant action assigned to the MA | MA Director |  |  |
|  | - Instructs the IB for follow-up of any relevant action assigned to the IB | Head of IB |  |  |
|  | - Ensure the filing of the minutes and any related documentation | Monitoring expert of Monitoring Unit |  | - PIM - Chapter K |

Model for submission to the Monitoring Committee
of  dd/mm/yy

- CF/ISPA monitoring sheet

All data in the report should be up to 30 June or 31 December

- 1A. PROJECT Identification

Name of project: CF/ISPA Financing Memorandum reference N°: MA/Implementing Agency: Rate of CF/ISPA assistance: Signature of Financing Memorandum- Commission - Country Amendment number - Commission - Country

- 1B. Managing Authority (MA)/Implementing Agency (IA)

Name: Address: Post Code: Town: Contact Name: Telephone No.: E-mail:

- 2. Brief chronological description of activities / works carried out

- 3. Specific conditions related to the Project (Article 8 of Financing Memorandum)

- Refer to specific conditions, if any, and state how they have been complied with as well as the date of fulfilment (the reference of the Commission correspondence acknowledging fulfilment of those conditions already complied with).

- 4.	Update of Procurement Plan

| Contract ( N°, Type & Description)* |  | Date of publication of tender forecast | Type of tender envisaged** | Date of publication of tender notice |  | Cost of contract /estimated cost of contract | Type of co-financing | Date of Signature and name of the company awarded/ State of Play*** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | If not published | If published | € million | Joint/ parallel |  |
|  |  |  |  | Estimated Date | Date, OJ Ref and Internet. |  |  |  |
| Signed |  |  |  |  |  |  |  |  |
| Under preparation |  |  |  |  |  |  |  |  |

(*)	Specify the main contract.

(**)	Indicate whether the contract agreement will be either Red, Yellow or Silver book.  Specify if it is a local, international or restricted tender and give justification for procedure in case of pre-qualification.

(***)	For the contracts under preparation, please give some details about the stage of preparation of the tender documents.

- 5.	Expenditure Plan		Unit: €

| Year | Total eligible cost |  | Actual Realised Payments |  | Future Estimated Expenditure |  | Total Expenditure |  | Divergence/ Total Cost% (9)=((7)-(2))/ /total (2) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Initial estimation* | Current accepted estimation** | (up to cut-off date) | (%) (3)/(2) | (as from cut-off date) | (%) (5)/(2) | (7)=(3)+(5) | (%) (7)/(2) |  |
|  | (1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) |
| 2000 |  |  |  |  |  |  |  |  |  |
| 2001 |  |  |  |  |  |  |  |  |  |
| 2002 Quarter 1 |  |  |  |  |  |  |  |  |  |
| Quarter 2 |  |  |  |  |  |  |  |  |  |
| Quarter 3 |  |  |  |  |  |  |  |  |  |
| Quarter 4 |  |  |  |  |  |  |  |  |  |
| 2003 Quarter 1 |  |  |  |  |  |  |  |  |  |
| Quarter 2 |  |  |  |  |  |  |  |  |  |
| Quarter 3 |  |  |  |  |  |  |  |  |  |
| Quarter 4 |  |  |  |  |  |  |  |  |  |
| 2004 |  |  |  |  |  |  |  |  |  |
| 2005 |  |  |  |  |  |  |  |  |  |
| 2006 |  |  |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |  |  |
| Proposed change to the Financial Plan Yes No Already submitted to the EC on: To be submitted to the EC on: To be presented at the Monitoring Committee (append plan and reasons for change) |  |  |  |  |  |  |  |  |  |

*	At the moment of the signature of the Financing Memorandum
**	Last Monitoring Committee

- 7. Reasons for differences (if any) between physical and financial execution Explanations for delays (if appropriate)

- 8. Technical, financial or legal problems (Annex III.1 of FM)

Refer to any problems that have arisen in the implementation of the measure, including departures from the original financial plan, and explain what action has been taken to correct them. Refer to any suspension, Financial correction and/or irregularity.

- 9. Observations and Recommendations of National and/or Community inspection authorities (Annex III.1 of FM)

Give summary observations or recommendations, if any, (with full reference to source), and state how they have been complied with.

- 10. Measures adopted to advertise Community Assistance (Annex III.6 of FM)

Billboards erected at the site? Yes No Media used to inform the public of the measure in hand: Press Television Radio Other audio-visual media Type of written documentation made available to the public:

- 11. Expected completion date

In initial FM (end date fixed in the initial FM) In Current FM (end date in modified FM) Expected completion date Modification of date to be proposed at MC: Yes No

| Name of project: | Insert as relevant |
| --- | --- |
| ISPA FM reference N°: | Insert as relevant signed on : Insert as relevant |

HOW TO USE THE CHECK-LIST : - The boxes  represent mandatory checks to be performed. - All persons assigned to perform controls must, for each control, tick the boxes in the column corresponding to their respective position. - Comments/notes may be added on the last page of the Check-list and must be cross-referenced (numbered) in the column “Note Ref.“ - The check-list must be signed by the performers of controls and reviewers once all controls are performed - The check-list must be used as follows: - In case of the projects implemented by the Ministry of Transport the check-list use the option “Preparation” below; - In case of the projects implemented by the Intermediate body (road projects) the check-list use the option “First control” below.

Stage 1 Preparation and First control by : Insert as relevant

Preparation/First control started on : Date : __ / __ / ___ at __ : __

| Control # | Items to be checked | Preparation/1st control | 2nd control | 3th control | Supervision | Supervision / Approval |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Monitoring expert | Head of Monitoring Unit | Head of Financial Control Unit | Head of Payments Dept | MA Director | Note Ref. |
|  | General format |  |  |  |  |  |  |
|  | - The format of CF/ISPA Monitoring Sheet is in line with the applicable standard format | -  | -  |  |  |  |  |
|  | - Cut-off date is mentioned and corresponds to the actual reporting period | -  | -  |  |  |  |  |
|  | 1a – Project identification |  |  |  |  |  |  |
|  | - Check : - Name of the Project - FM Reference - Rate of CF/ISPA Assistance - Dates of signature of CF/ISPA FM | -  | -  |  |  |  |  |
|  | - Is there any Amendment to the CF/ISPA FM ? - If so : information on Amendment number and dates of signatures are reported and are correct | -  | -  |  |  |  |  |
|  | 1b Managing Authority/Implementing Agency |  |  |  |  |  |  |
|  | - Information on the Managing Authority/Implementing Agency is complete and correct | -  | -  |  |  |  |  |
|  | 2 – Chronological description of activities / works carried out |  |  |  |  |  |  |
|  | - Activities/works carried out are properly described and take into account all relevant information up to cut-off date - Check also evolution since the previous Monthly Progress Sheet and Monitoring Sheet | -  | -  |  |  |  |  |
|  | 3 – Specific conditions related to the Project (Article 8 of CF/ISPA FM) |  |  |  |  |  |  |
|  | - Reconcile the information with the CF/ISPA FM : status of the conditions are properly described and take into account all relevant information up to cut-off date - Check also evolution since the previous Monthly Progress Sheet and Monitoring Sheet | -  | -  |  |  |  |  |
|  | 4 – Up date of Procurement Plan |  |  |  |  |  |  |
|  | - The procurement plan is reconciled with the Internal detailed Procurement Plan of the MA/IA - Check also evolution since the previous Monthly Progress Sheet and Monitoring Sheet | -  | -  |  |  |  |  |
|  | - If there is a need of modification of the procurement procedure envisaged, a formal request should be included in the Monitoring Sheet and stated in the presentation of the project | -  | -  |  |  |  |  |
|  | 5 – Expenditure Plan |  |  |  |  |  |  |
|  | - The data in the Expenditure plan are correct - Reconcile the figures with the Monthly Financial Report of the MA/IA and Accounting system - Check also evolution since the previous Monthly Progress Sheet and Monitoring Sheet |  |  | -  | -  |  |  |
|  | 6 – Advanced information sheet for physical and Financial Execution |  |  |  |  |  |  |
|  | - The data are correct - Reconcile the figures with : - Engineer / contractor reports - Monthly Financial Report - Accounting system - Check also evolution since the previous Monthly Progress Sheet and Monitoring Sheet | -  | -  | -  | -  |  |  |
|  | 7 – Reasons for differences (if any) between physical and Financial Execution (Explanation for delays) |  |  |  |  |  |  |
|  | - and |  |  |  |  |  |  |
|  | 8 – Technical, Financial or Legal problems (Annex III.1 of FM) |  |  |  |  |  |  |
|  | - and |  |  |  |  |  |  |
|  | 9 – Observations and recommendations of national and/or Community inspection authorities |  |  |  |  |  |  |
|  | - Check evolution since the previous Monthly Progress Sheet and Monitoring Sheet - Reconcile the information with any recent Audit Report in relation to the Measure under report - References (dates / reference number / audit institution) of the Audit reports must be reported here : - ………………………………………………….. - ………………………………………………….. - ………………………………………………….. | -  | -  |  |  |  |  |
|  | 10 – Measures adopted to advertise Community Assistance(Annex III.6 of CF/ISPA FM) |  |  |  |  |  |  |
|  | - Measures related to publicity are properly described and take into account all relevant information up to cut-off date - Check also evolution since the previous Monthly Progress Sheet and Monitoring Sheet | -  | -  |  |  |  |  |
|  | 11 – Expected completion date |  |  |  |  |  |  |
|  | - Reconcile the dates with : - Initial FM - Amendment to FM - Previous Monthly Progress Sheet and Monitoring Sheet - Information provided under headings: - 5 – Reasons for differences (if any) between physical and Financial Execution (Explanation for delays) - and - 6 – Technical, Financial or Legal problems (Annex III.1 of FM) | -  | -  |  |  |  |  |
|  | 12 - Supervision |  |  |  | -  | -  |  |

|  | Transmission to Second Control Name / Project Coordinator / Signature Date: Hour : : . |
| --- | --- |

| Stage 2 Second control by : Head of Monitoring Unit |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |
|  | # Controls started on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | - Performs controls as assigned in column “Second control” |  | -  |  |  |
| --- | --- | --- | --- | --- | --- |

|  | Transmission to Third Control Name / Head of Monitoring Unitn / Signature Date: Hour : : . |
| --- | --- |

| Stage 3 Third control by : Head of Financial Control Unit |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |
|  | # Controls started on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | - Performs controls as assigned in column “Third control” |  | -  |  |  |
| --- | --- | --- | --- | --- | --- |

|  | Transmission to Supervision Name / Head of Financial Control Unit/ Signature: Date: Hour : : . |
| --- | --- |

| Stage 4 Supervision by : Head of Payments Department |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |
|  | # Controls started on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | - Performs controls as assigned in column “Second control” |  | -  |  |  |
| --- | --- | --- | --- | --- | --- |

|  | Transmission to Supervision / Approval Name / Head of Payments Department Signature: Date: Hour : : . |
| --- | --- |

| Stage 5 Supervision / Approval by : Director CPPD |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | - Review performed as assigned in column “Supervision” |  |  | -  |  |
| --- | --- | --- | --- | --- | --- |

|  | Approval : Name / Director CPPD Signature: Date: Hour : : . |
| --- | --- |

NOTES / COMMENTS / INSTRUCTIONS :

| Insert as relevant | Insert as relevant |
| --- | --- |
| Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : | Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : |
| Insert as relevant | Insert as relevant |
| Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : | Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : |
| Insert as relevant | Head of MA |
| Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : | Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : |

| INTERNAL AUDIT : This area is dedicated to comments / notes / references / etc…. of internal auditors |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ref | Date | Name | Comments | Signature |