Purpose

To establish the procedure for preparation and submission of the CF (CR 1164/94)/ISPA Final Report which must be submitted by the Head of MA to NC and Head of PA/NF and which will serve for the closure of CF (CR 1164/94)/ISPA projects.

Background

The Final Report is a report required by the EC to be submitted with the Final Application for payment.

Procedure

| # | Action | Function / Person responsible | Timing / Deadline | Standard Form / Template |
| --- | --- | --- | --- | --- |
|  | - PREPARATION OF THE CF (CR 1164/94)/ISPA FINAL REPORT |  |  |  |
|  | - Request the Head of MA/IA to start the preparation of the Final Report - Specify the deadline for receiving the Final Report to be prepared by the MA | Head of PA/NF |  |  |
|  | - Transmits to the management of the MA the instructions of the Head of PA/NF | Head of MA |  |  |
|  | - Taking into account factors such as workload and segregation of duties, assigns the task of preparation of the Final Report to Monitoring Expert | MA Director |  |  |
|  | - For each ISPA FM assigned to him/her, prepares : - - An CF (CR 1164/94)/ISPA Final Report using standard format - - A Check list – Control of CF (CR 1164/94)/ISPA Final Report | Monitoring Expert of Monitoring Unit | - Day of receipt of task | - G04 - 01 - Standard format : ISPA Final Report |
|  | - Performs controls of the CF (CR 1164/94)/ISPA Final Report as assigned in the Check list and formalises controls on the Check-list. If any problem is noticed, consult with relevant colleague, IB, Engineer, Contractor in order to obtain further information / documents and requests any clarification | Monitoring Expert of Monitoring Unit |  | - G03 - 02 - Check-list : Control of ISPA Final Report |
|  | - For each ISPA FM assigned to the IB (road projects), should be prepared: - - An CF (CR 1164/94)/ISPA Final Report using standard format - - A Check list – Control of CF (CR 1164/94)/ISPA Final Report | Expert within the IB appointed by the Head of IB | - Day of receipt of task | - IB’s Manual |
|  | - Performs controls of the CF (CR 1164/94)/ISPA Final Report as assigned in the Check list and formalises controls on the Check-list. If any problem is noticed, consult with relevant colleague, Engineer, Contractor, MA staff in order to obtain further information / documents and requests any clarification | Expert within the IB appointed by the Head of IB |  | - IB’s Manual |
|  | - Head of IB transmits the CF (CR 1164/94)/ISPA Final Report to the MA | Head of IB | - Within 5 months of completion of the project |  |
|  | - The CF (CR 1164/94)/ISPA Final Report prepared and submitted by the IB are following the standard procedure described below. | MA |  |  |
|  | - In case of irregularities, initiates relevant procedures | Project Coordinator of Tendering and Contracting for CF 1164/94 Department |  | - PIM - Chapter J - Irregularities |
|  | Signs the Check-list and transmits Check-list + CF (CR 1164/94)/ISPA Final Report to Head of Monitoring Unit | Monitoring Expert of Monitoring Unit |  |  |
|  | - CONTROL OF THE FINAL REPORT |  |  |  |
|  | - Performs controls of the CF (CR 1164/94) /ISPA Final Report as assigned in the Check list and formalises controls on the Check-list; - Discuss with the Project Coordinator any relevant issue | Head of Monitoring Unit | - Day of receipt |  |
|  | - Performs controls of the CF (CR 1164/94)/ISPA Final Report as assigned in the Check list and formalises controls on the Check-list; - Discuss with the Project Coordinator any relevant issue | Head of Financial Control Unit |  |  |
|  | - Performs controls of the CF (CR 1164/94)/ISPA Final Report as assigned in the Check list and formalises controls on the Check-list; - Discuss with the Head of Financial Control Unit any relevant issue | Head of Payments Department |  |  |
|  | - In case of irregularities, initiates relevant procedures | Head of Tendering and Contracting for CF 1164/94 Department |  | - PIM - Chapter J - Irregularities |
|  | - Signs the Check-list and transmits Check-list + CF (CR 1164/94)/ISPA Final Report to Director of MA | Head of Monitoring Unit |  |  |
|  | - SUPERVISION OF THE FINAL REPORT |  |  |  |
|  | - Review the CF (CR 1164/94)/ISPA Final Report and the Check list and formalises the review | Director of MA /Deputy Head of MA | - Day of receipt |  |
|  | - In case of irregularities, initiates relevant procedures | Director of MA/Deputy Head of MA |  | - PIM - Chapter J - Irregularities |
|  | - Signs the Checklist to CF (CR 1164/94)/ISPA Final Report | Director of MA /Deputy Head of MA |  |  |
|  | - Transmits Check-list + ISPA (CR 1164/94) Final Report to Head of MA/IA | Director of MA /Deputy Head of MA |  |  |
|  | - APPROVAL OF THE FINAL REPORT |  |  |  |
|  | - Signs the Checklist to CF (CR 1164/94)/ISPA Final Report | Head of MA | - Day of receipt |  |
|  | - Transmits Check-list + CF (CR 1164/94)/ISPA Final Report back to Project Coordinator for entering in MIS | Head of MA |  |  |
|  | - TRANSMISSION OF THE FINAL REPORT |  |  |  |
|  | - Ensures the transmission of the CF (CR 1164/94)/ISPA Final Report; - Electronic version to the NC and Head of PA/NF through the CF/ISPA MIS | Monitoring expert of Monitoring Unit | - Upon deadline specified by the Head of PA/NF |  |
|  | - Files a copy of the CF (CR 1164/94)/ISPA Final Report entered into MIS + Check-list | Monitoring expert of Monitoring Unit |  | - PIM - Chapter K |
|  | - COMMENTS OF THE FINAL REPORT |  |  |  |
|  | - Receives comments (if any) from the NC services and PA/NF via MIS | Monitoring expert of Monitoring Unit |  |  |
|  | - Ensures the modification of the CF (CR 1164/94)/ISPA Final Report until finalisation by applying procedure starting from point 1.2 | Monitoring expert of Monitoring Unit | - Day of receipt of comments |  |
|  | - Ensures that the final version of the CF Final Report is signed by the Head of MA | Director of the MA |  |  |
|  | - Ensures the transmission of the final version of the CF (CR 1164/94)/ISPA Final Report - Electronic version to the NC and Head of PA/NF through the CF/ISPA MIS - Original hard copy to the NC services - Original hard copy to the PA/NF for compilation for Final Application Payment (procedures in PA/NF manual) | Head of Monitoring Unit | - By the date specified by the Paying Authority/NF | - G04 - 01 - Standard format : Final Report |

- CF/ISPA FINAL REPORT

Cut-off date :  dd/mm/yy

- 1A. PROJECT Identification

Name of project: CF/ISPA Financing Memorandum reference N°: MA/Implementing Agency: Rate of CF/ISPA assistance: Signature of Financing Memorandum- Commission - Country Amendment number - Commission - Country

- 1B. Managing Authority (MA)/Implementing Agency (IA)

Name: Address: Post Code: Town: Contact Name: Telephone No.: E-mail:

- 2. Brief chronological description of activities / works carried out

- 3. Specific conditions related to the Project (Article 8 of Financing Memorandum)

- Refer to specific conditions, if any, and state how they have been complied with as well as the date of fulfilment (the reference of the Commission correspondence acknowledging fulfilment of those conditions already complied with).

- 4.	Update of Procurement Plan

| Contract ( N°, Type & Description)* |  | Date of publication of tender forecast | Type of tender envisaged** | Date of publication of tender notice |  | Cost of contract /estimated cost of contract | Type of co-financing | Date of Signature and name of the company awarded/ State of Play*** |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | If not published | If published | € million | Joint/ parallel |  |
|  |  |  |  | Estimated Date | Date, OJ Ref and Internet. |  |  |  |
| Signed |  |  |  |  |  |  |  |  |
| Under preparation |  |  |  |  |  |  |  |  |

(*)	Specify the main contract.

(**)	Indicate whether the contract agreement will be either Red, Yellow or Silver book.  Specify if it is a local, international or restricted tender and give justification for procedure in case of pre-qualification.

(***)	For the contracts under preparation, please give some details about the stage of preparation of the tender documents.

- 5.	Expenditure Plan		Unit: €

| Year | Total eligible cost |  | Actual Realised Payments |  | Total Expenditure |  | Divergence/ Total Cost% (9)=((7)-(2))/ /total (2) |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Initial estimation* | Current accepted estimation** | (up to cut-off date) | (%) (3)/(2) | (7)=(3)+(5) | (%) (7)/(2) |  |
|  | (1) | (2) | (3) | (4) | (7) | (8) | (9) |
| 2000 |  |  |  |  |  |  |  |
| 2001 |  |  |  |  |  |  |  |
| 2002 Quarter 1 |  |  |  |  |  |  |  |
| Quarter 2 |  |  |  |  |  |  |  |
| Quarter 3 |  |  |  |  |  |  |  |
| Quarter 4 |  |  |  |  |  |  |  |
| 2003 Quarter 1 |  |  |  |  |  |  |  |
| Quarter 2 |  |  |  |  |  |  |  |
| Quarter 3 |  |  |  |  |  |  |  |
| Quarter 4 |  |  |  |  |  |  |  |
| 2004 |  |  |  |  |  |  |  |
| 2005 |  |  |  |  |  |  |  |
| 2006 |  |  |  |  |  |  |  |
| Total |  |  |  |  |  |  |  |

*	At the moment of the signature of the Financing Memorandum
**	Last Application for payment

- 7. Reasons for differences (if any) between physical and financial execution Explanations for delays (if appropriate)

- 8. Technical, financial or legal problems (Annex III.1 of FM)

Refer to any problems that have arisen in the implementation of the measure, including departures from the original financial plan, and explain what action has been taken to correct them. Refer to any suspension, Financial correction and/or irregularity.

- 9. Observations and Recommendations of National and/or Community inspection authorities (Annex III.1 of FM)

Give summary observations or recommendations, if any, (with full reference to source), and state how they have been complied with.

- 10. Measures adopted to advertise Community Assistance (Annex III.6 of FM)

Billboards erected at the site? Yes No Media used to inform the public of the measure in hand: Press Television Radio Other audio-visual media Type of written documentation made available to the public:

- 11. An indication of the way in which the measure will be managed once completed

- 12. Confirmation, if appropriate, of financial forecasts, especially as regards operating costs and expected revenues

- 13. Confirmation of the socio-economic forecasts, especially the expected costs and benefits

- 14. An indication of the actions taken to ensure protection of the environment and their cost including compliance with the polluter-pay principles

- 15. Completion date

In initial FM (end date fixed in the initial FM) In Current FM (end date in modified FM) The date at which the measure became operational

| Name of measure: | Insert as relevant |
| --- | --- |
| CF/ISPA FM reference N°: | Insert as relevant signed on : Insert as relevant |

HOW TO USE THE CHECK-LIST : - The boxes  represent mandatory checks to be performed. - All persons assigned to perform controls must, for each control, tick the boxes in the column corresponding to their respective position. - Comments/notes may be added on the last page of the Check-list and must be cross-referenced (numbered) in the column “Note Ref.“ - The check-list must be signed by the performers of controls and reviewers once all controls are performed - The check-list must be used as follows: - In case of the projects implemented by the Ministry of Transport the check-list use the option “Preparation” below; - In case of the projects implemented by the Intermediate body (road projects) the check-list use the option “First control” below.

Stage 1 Preparation and First control by : Insert as relevant

Preparation/First control started on : Date : __ / __ / ___ at __ : __

| Control # | Items to be checked | Preparation/1st control | 2nd control | 3 th control | Supervision | Supervision / Approval |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Monitoring expert | Head of Monitoring Unit | Head of Financial Control Unit | Head of Payments Department | MA Director/Deputy Head of MA/Head of MA | Note Ref. |
|  | General format |  |  |  |  |  |  |
|  | - The format of CF/ISPA Final Report is in line with the applicable standard format | -  | -  |  |  |  |  |
|  | - Cut-off date is mentioned and corresponds to the actual reporting period | -  | -  |  |  |  |  |
|  | 1a – Measure identification |  |  |  |  |  |  |
|  | - Check : - Name of the Measure - FM Reference - Rate of ISPA Assistance - Dates of signature of CF/ISPA FM | -  | -  |  |  |  |  |
|  | - Is there any Amendment to the CF/ISPA FM ? - If so : information on Amendment number and dates of signatures are reported and are correct | -  | -  |  |  |  |  |
|  | 1b – Implementing Agency |  |  |  |  |  |  |
|  | - Information on the Managing Authority/Implementing Agency is complete and correct | -  | -  |  |  |  |  |
|  | 2 – Chronological description of activities / works carried out |  |  |  |  |  |  |
|  | - Activities/works carried out are properly described and take into account all relevant information up to cut-off date - Check also evolution since the previous Monthly Progress Sheet and Monitoring Sheet | -  | -  |  |  |  |  |
|  | 3 – Specific conditions related to the Measure (Article 8 of ISPA FM) |  |  |  |  |  |  |
|  | - Reconcile the information with the CF/ISPA FM : status of the conditions are properly described and take into account all relevant information up to cut-off date - Check also evolution since the previous Monthly Progress Sheet and Monitoring Sheet | -  | -  |  |  |  |  |
|  | 4 – Up date of Procurement Plan |  |  |  |  |  |  |
|  | - The procurement plan is reconciled with the Internal detailed Procurement Plan of the MA/IA - Check also evolution since the previous Monthly Progress Sheet and Monitoring Sheet | -  | -  |  |  |  |  |
|  | 5 – Expenditure Plan |  |  |  |  |  |  |
|  | - The data in the Expenditure plan are correct - Reconcile the figures with the Accounting system - Check also evolution since the previous Monthly Progress Sheet and Monitoring Sheet |  |  | -  |  |  |  |
|  | 6 – Advanced information sheet for physical and Financial Execution |  |  |  |  |  |  |
|  | - The data are correct - Reconcile the figures with : - Engineer / contractor reports - Accounting system - Check also evolution since the previous Monthly Progress Sheet and Monitoring Sheet | -  | -  | -  |  |  |  |
|  | 7 – Reasons for differences (if any) between physical and Financial Execution (Explanation for delays) |  |  |  |  |  |  |
|  | - and |  |  |  |  |  |  |
|  | 8 – Technical, Financial or Legal problems (Annex III.1 of FM) |  |  |  |  |  |  |
|  | - and |  |  |  |  |  |  |
|  | 9 – Observations and recommendations of national and/or Community inspection authorities |  |  |  |  |  |  |
|  | - Check evolution since the previous Monthly Progress Sheet and Monitoring Sheet - Reconcile the information with any recent Audit Report in relation to the Measure under report - References (dates / reference number / audit institution) of the Audit reports must be reported here : - ………………………………………………….. - ………………………………………………….. - ………………………………………………….. | -  | -  |  |  |  |  |
|  | 10 – Measures adopted to advertise Community Assistance(Annex III.6 of CF/ISPA FM) |  |  |  |  |  |  |
|  | - Measures related to publicity are properly described and take into account all relevant information up to cut-off date - Check also evolution since the previous Monthly Progress Sheet and Monitoring Sheet | -  | -  |  |  |  |  |
|  | - 11. An indication of the way in which the measure will be managed once completed |  |  |  |  |  |  |
|  | - Sufficient and quality description of the future management of the measure | -  | -  |  |  |  |  |
|  | - 12. Confirmation, if appropriate, of financial forecasts, especially as regards operating costs and expected revenues |  |  |  |  |  |  |
|  | - Sufficient and quality confirmation of financial forecasts and operating costs and revenues |  |  | -  | -  |  |  |
|  | - 13. Confirmation of the socio-economic forecasts, especially the expected costs and benefits |  |  |  |  |  |  |
|  | - Sufficient and quality confirmation of socio-economic forecasts, costs and benefits | -  | -  |  |  |  |  |
|  | - 14. An indication of the actions taken to ensure protection of the environment and their cost including compliance with the polluter-pay principles |  |  |  |  |  |  |
|  | - Sufficient and quality information on the actions taken to ensure protection of environment | -  | -  |  |  |  |  |
|  | 15 Completion date |  |  |  |  |  |  |
|  | - Reconcile the dates with : - Initial FM - Amendment to FM - The date the measure became operational | -  | -  |  |  |  |  |
|  | - 16. Supervision |  |  |  | -  | -  |  |

|  | Transmission to Second Control Name / Monitoring Expert / Signature Date: Hour : : . |
| --- | --- |

| Stage 2 Second control by : Head of Monitoring Unit |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |
|  | # Controls started on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | - Performs controls as assigned in column “Second control” |  | -  |  |  |
| --- | --- | --- | --- | --- | --- |

|  | Name / Head of Monitoring Unit Signature: Transmission to Third Control Date: Hour : : . |
| --- | --- |

| Stage 3 Third control by: Head of Financial Control Unit |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |
|  | # Controls started on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | - Performs controls as assigned in column “Second control” |  | -  |  |  |
| --- | --- | --- | --- | --- | --- |

|  | Name / Head of Financial Control Unit Signature: Transmission to Supervision Date: Hour : : . |
| --- | --- |

| Stage 4 Supervision by : Head of Payments Department |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |
|  | # Controls started on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | - Performs controls as assigned in column “Second control” |  | -  |  |  |
| --- | --- | --- | --- | --- | --- |

|  | Transmission to Supervision / Approval Name / Head of Payments Department Signature: Date: Hour : : . |
| --- | --- |

| Stage 5 Supervision / Approval by : Director/Deputy Head of MA/IA/Head of MA /IA |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | # Documents received on : Date : __ / __ / ___ at __ : __ |  |  |  |  |

|  | - Review performed as assigned in column “Supervision” |  |  | -  |  |
| --- | --- | --- | --- | --- | --- |

|  | Approval : Name / MA/IA Director /Deputy Head of MA /IA Signature: Date: Hour : : . |
| --- | --- |

|  | Final Approval : Name / Head of MA /IA Signature: Date: Hour : : . |
| --- | --- |

NOTES / COMMENTS / INSTRUCTIONS :

| Insert as relevant | Insert as relevant |
| --- | --- |
| Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : | Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : |
| Insert as relevant | Insert as relevant |
| Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : | Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : |
| Insert as relevant |  |
| Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : | Reference (to be reported in the column Note Ref) and Content of the notes / comments / instructions : |

| INTERNAL AUDIT : This area is dedicated to comments / notes / references / etc…. of internal auditors |  |  |  |  |
| --- | --- | --- | --- | --- |
| Ref | Date | Name | Comments | Signature |